## README
API Ingestion Engine – Complete Productionization Project Plan
How to use
1) Go to the Inputs tab and set the Planned Start Date and horizon.
2) Use the Master tab to filter by Category (Policy/Process/Procedure/Design/Implementation), Workstream, or Phase.
3) Policy/Process/Procedure/Design/Implementation tabs are curated views for governance and delivery tracking.
4) Update Status and Notes/Evidence Link as work progresses; dates calculate automatically.
5) Use the Gantt tab for a week-based view of key deliverables and milestones.
Conventions
- P0–P3 = incident/defect priority aligned to the Severity Policy task (PLY-02).
- Effort is in person-days (estimates). Duration is in calendar days for scheduling (adjust if you prefer business-day scheduling).
- Dependencies use Task IDs (comma-separated).
Core operational artifacts included
- Policies, processes, procedures/runbooks, operations handbook, alerting & on-call model, credential rotation, CI/CD promotion gates, audit/lineage, DQ/DLQ/replay.

## Inputs
API Ingestion Engine – Program Inputs
Edit the blue cells only
Planned Start Date | 2026-02-23 | Date the plan starts (edit this).
Days per Week (for schedule) | 7 | Used to convert weeks → dates.
Plan Horizon (weeks) | 24 | Used for the Gantt view.
Workdays per Week (for effort planning) | 5 | Used for capacity (optional).
Default Timezone | Australia/Sydney | Reference timezone for ops.

## Master
Master – Work Breakdown Structure (WBS)
Update Status and Notes/Evidence Link during execution. Dates auto-calc from Inputs.
Task ID | Category | Workstream | Phase | Module | Task Name | Task Description | Deliverable/Artifact | Owner Role | RACI | Priority | Status | Est Effort (Person-days) | Duration (days) | Start Week | End Week | Start Date | End Date | Dependencies | Milestone (Y/N) | Notes/Evidence Link
DSN-01 | Design | Architecture | 0 | Reference Architecture | Define target reference architecture | Define control plane, compute model, bronze contract, orchestration, observability, security, lineage, and environments. | Architecture diagram + ADRs | Data Platform Architect | A | P0 | Not Started | 8 | 10 | 1 | 2 | 2026-02-23 | 2026-03-04 | PLY-01 | N
DSN-02 | Design | Control Plane | 1 | Metadata Registry | Design control plane schema (sources/endpoints/state/runs/errors) | Define Delta table schemas, keys, partitioning, indexing strategy, ownership fields, SLO fields. | Control plane data model spec | Data Platform Architect | A | P0 | Not Started | 6 | 7 | 2 | 2 | 2026-03-02 | 2026-03-08 | DSN-01 | N
DSN-03 | Design | Connector SDK | 1 | Connector Interface | Design connector SDK interface & packaging | Define connector contract methods, error handling conventions, versioning, and packaging (wheel). | Connector SDK spec | Data Engineer | R | P0 | Not Started | 5 | 6 | 2 | 2 | 2026-03-02 | 2026-03-07 | DSN-01 | N
DSN-04 | Design | Runtime | 1 | Extraction Runtime | Design extraction runtime behaviors | Retry/backoff, pagination patterns, throttling, circuit breaker, incremental strategies, idempotency/dedupe. | Runtime design spec | Data Engineer | R | P0 | Not Started | 6 | 7 | 3 | 3 | 2026-03-09 | 2026-03-15 | DSN-03 | N
DSN-05 | Design | Bronze | 1 | Bronze Contract | Design Bronze table contract | Define required metadata columns, raw payload storage type, partitioning, naming, retention hooks. | Bronze contract spec | Data Platform Architect | A | P0 | Not Started | 4 | 5 | 3 | 3 | 2026-03-09 | 2026-03-13 | DSN-02 | N
DSN-06 | Design | Orchestration | 1 | Scheduling | Design orchestration approach | Controller job vs job-per-source strategy, concurrency controls, scheduling, backfill workflow pattern. | Orchestration design spec | Data Platform Architect | A | P1 | Not Started | 4 | 5 | 3 | 3 | 2026-03-09 | 2026-03-13 | DSN-01 | N
DSN-16 | Design | Compute | 1 | Compute Policies | Design compute model & cluster policies | Define cluster/job compute, autoscaling, instance types, cost controls, cluster policies. | Compute policy design | DevOps/Platform Eng | A | P1 | Not Started | 3 | 4 | 4 | 4 | 2026-03-16 | 2026-03-19 | DSN-01 | N
DSN-18 | Design | Testing | 1 | Test Strategy | Design testing strategy (unit/integration/contract) | Define test harness, mocking patterns, golden responses, env gates, and smoke tests. | Test strategy doc | QA/Test | A | P1 | Not Started | 4 | 5 | 4 | 4 | 2026-03-16 | 2026-03-20 | DSN-03,DSN-14 | N
DSN-07 | Design | Security | 2 | Secrets & Identity | Design secrets integration & auth patterns | External secret manager integration, secret naming conventions, OAuth2 flows, token caching/refresh patterns. | Security & auth design spec | Security/Identity Eng | A | P0 | Not Started | 5 | 6 | 3 | 3 | 2026-03-09 | 2026-03-14 | PLY-03,DSN-03 | N
DSN-14 | Design | DevSecOps | 2 | CI/CD | Design CI/CD pipeline and IaC approach | Define tests, scanning, artifacts, deployment strategy, environment configs, approval gates, Terraform modules. | CI/CD & IaC design spec | DevOps/Platform Eng | A | P0 | Not Started | 6 | 7 | 4 | 4 | 2026-03-16 | 2026-03-22 | PLY-07,PLY-08 | N
DSN-15 | Design | Governance | 2 | Documentation | Design operations handbook structure | Define handbook sections: architecture, SLOs, dashboards, alerts, runbooks, on-call, escalation. | Ops handbook outline | SRE/Operations | A | P1 | Not Started | 3 | 3 | 6 | 6 | 2026-03-30 | 2026-04-01 | PRC-01,DSN-01 | N
DSN-17 | Design | Governance | 2 | Retention Implementation | Design retention purge implementation | Define purge job patterns, legal hold exceptions, and verification reporting. | Purge design spec | Data Engineer | R | P2 | Not Started | 3 | 4 | 6 | 6 | 2026-03-30 | 2026-04-02 | PLY-06 | N
DSN-08 | Design | Observability | 3 | Metrics Model | Design metrics/logging schema for observability | Define run metrics, API metrics, freshness metrics, DQ results, error taxonomy, and dimensions. | Observability data model spec | SRE/Operations | A | P0 | Not Started | 5 | 6 | 4 | 4 | 2026-03-16 | 2026-03-21 | DSN-02,PLY-09 | N
DSN-09 | Design | Alerting | 3 | Alerts | Design alert rules & routing mappings | Define alert conditions, thresholds, mapping to P0-P3, routing to platform vs domain owners, suppression logic. | Alert rules design | SRE/Operations | A | P0 | Not Started | 4 | 5 | 5 | 5 | 2026-03-23 | 2026-03-27 | DSN-08,PLY-02 | N
DSN-10 | Design | Data Quality | 3 | DQ Framework | Design DQ framework at ingest boundary | Define rule types, severity levels (warn/quarantine/fail), configuration storage, and reporting. | DQ design spec | Data Engineer | R | P1 | Not Started | 4 | 5 | 5 | 5 | 2026-03-23 | 2026-03-27 | DSN-02 | N
DSN-11 | Design | DLQ/Replay | 3 | Error Handling | Design DLQ and replay mechanisms | Define DLQ table schema, replay job patterns, replay by run_id/window, and audit logging. | DLQ/Replay design spec | Data Engineer | R | P1 | Not Started | 4 | 5 | 5 | 5 | 2026-03-23 | 2026-03-27 | DSN-10 | N
DSN-12 | Design | Schema Evolution | 3 | Schema Drift | Design schema drift detection and evolution policy | Define detection approach, versioning, breaking change handling, quarantine workflows and alerts. | Schema drift design spec | Data Platform Architect | A | P1 | Not Started | 4 | 5 | 6 | 6 | 2026-03-30 | 2026-04-03 | DSN-05,PLY-14 | N
DSN-13 | Design | Lineage | 3 | Audit & Lineage | Design auditing and lineage approach | Define audit events, evidence tables, UC lineage usage, optional OpenLineage emission pattern. | Audit & lineage design spec | Data Platform Architect | A | P1 | Not Started | 4 | 5 | 6 | 6 | 2026-03-30 | 2026-04-03 | PLY-16 | N
DSN-19 | Design | Onboarding Factory | 4 | Templates | Design onboarding templates and automation | Define config templates, vendor profiles, bulk onboarding approach and validation rules. | Onboarding templates design | Data Engineer | R | P1 | Not Started | 4 | 5 | 7 | 7 | 2026-04-06 | 2026-04-10 | PRC-06,PRC-13 | N
DSN-20 | Design | Cost/FinOps | 5 | Cost Attribution | Design cost attribution per source | Define how to attribute compute/storage to sources (tags, job run metadata) and dashboard. | Cost attribution design | DevOps/Platform Eng | A | P2 | Not Started | 3 | 4 | 10 | 10 | 2026-04-27 | 2026-04-30 | DSN-08 | N
IMP-01 | Implementation | Planning | 0 | Discovery | Inventory current API ingestions & patterns | Catalogue existing sources/endpoints/auth/pagination; group into patterns; identify pilot candidates. | API inventory + pattern matrix | Data Engineer | R | P1 | Not Started | 6 | 8 | 1 | 2 | 2026-02-23 | 2026-03-02 | PLY-01 | N | Include rate limits, volumes, SLAs where known.
IMP-02 | Implementation | Planning | 0 | Discovery | Define Tier-0/1/2 source list | Create initial tiering with business owners and SLO expectations. | Tiered source list | Product Owner | A | P1 | Not Started | 3 | 4 | 2 | 2 | 2026-03-02 | 2026-03-05 | PRC-15 | N
IMP-03 | Implementation | Control Plane | 1 | Metadata Registry | Implement registry Delta tables (sources/endpoints/state/runs/errors) | Create schemas in UC, apply permissions, implement migrations/versioning approach. | Control plane tables in UC | Data Engineer | R | P0 | Not Started | 8 | 10 | 3 | 4 | 2026-03-09 | 2026-03-18 | DSN-02,PLY-11 | N
IMP-05 | Implementation | Connector SDK | 1 | Connector Interface | Build connector SDK base package | Implement interfaces, standard exceptions, logging hooks, metrics hooks and packaging. | Connector SDK v1 | Data Engineer | R | P0 | Not Started | 10 | 12 | 3 | 4 | 2026-03-09 | 2026-03-20 | DSN-03,DSN-18 | N
IMP-55 | Implementation | Architecture | 1 | Reviews | Architecture review & signoff | Review architecture and ADRs with stakeholders; capture decisions and action items. | Architecture signoff | Data Platform Architect | A | P1 | Not Started | 2 | 2 | 3 | 3 | 2026-03-09 | 2026-03-10 | DSN-01 | Y
IMP-04 | Implementation | Control Plane | 1 | Metadata Registry | Implement config validation and publish pipeline | Build CI job to validate configs and publish to registry tables in each environment. | Config publish pipeline | DevOps/Platform Eng | R | P1 | Not Started | 6 | 8 | 4 | 5 | 2026-03-16 | 2026-03-23 | DSN-14,PRC-13 | N
IMP-06 | Implementation | Connector SDK | 1 | Connector Templates | Implement connector template: REST API key | Provide reusable template supporting headers, params, pagination and incremental watermark. | REST API key connector template | Data Engineer | R | P1 | Not Started | 5 | 6 | 4 | 4 | 2026-03-16 | 2026-03-21 | IMP-05 | N
IMP-07 | Implementation | Connector SDK | 1 | Connector Templates | Implement connector template: OAuth2 client credentials | Template for OAuth2 flows with token caching/refresh; supports vendor profiles. | OAuth2 connector template | Data Engineer | R | P0 | Not Started | 6 | 7 | 4 | 4 | 2026-03-16 | 2026-03-22 | IMP-05,IMP-16 | N
IMP-08 | Implementation | Runtime | 1 | Extraction Runtime | Implement HTTP client with retries/backoff/jitter | Standard HTTP layer handling 429/5xx/4xx policies and telemetry. | Resilient HTTP client | Data Engineer | R | P0 | Not Started | 6 | 7 | 4 | 4 | 2026-03-16 | 2026-03-22 | DSN-04 | N
IMP-13 | Implementation | Bronze | 1 | Bronze Contract | Create Bronze databases/schemas and naming conventions | Set up UC catalogs/schemas for bronze and ingestion control tables; permission templates. | UC schemas + conventions applied | Data Platform Architect | A | P0 | Not Started | 4 | 5 | 4 | 4 | 2026-03-16 | 2026-03-20 | DSN-05,PLY-11 | N
IMP-09 | Implementation | Runtime | 1 | Extraction Runtime | Implement pagination strategies | Support page number, next-token, cursor-based pagination as configurable strategies. | Pagination module | Data Engineer | R | P0 | Not Started | 6 | 7 | 5 | 5 | 2026-03-23 | 2026-03-29 | IMP-08 | N
IMP-10 | Implementation | Runtime | 1 | Extraction Runtime | Implement incremental load strategies + checkpointing | Support watermark timestamp, since_id, delta token; persist checkpoints in ingestion.state. | Incremental + checkpoint module | Data Engineer | R | P0 | Not Started | 7 | 9 | 5 | 6 | 2026-03-23 | 2026-03-31 | IMP-03,IMP-08 | N
IMP-14 | Implementation | Bronze | 1 | Bronze Contract | Implement Bronze writer (Delta) with metadata columns | Write raw_payload + ingest metadata; idempotency with payload_hash/record_id; batch write patterns. | Bronze writer module | Data Engineer | R | P0 | Not Started | 6 | 8 | 5 | 6 | 2026-03-23 | 2026-03-30 | IMP-13,DSN-05 | N
IMP-11 | Implementation | Runtime | 1 | Extraction Runtime | Implement rate limiting / throttling controls | Global concurrency limits + per-vendor QPS caps; config-driven. | Throttling module | Data Engineer | R | P1 | Not Started | 5 | 6 | 6 | 6 | 2026-03-30 | 2026-04-04 | IMP-08,DSN-20 | N
IMP-12 | Implementation | Runtime | 1 | Extraction Runtime | Implement circuit breaker & vendor outage handling | Stop hammering failing vendors; mark degraded; auto-recover; emit alerts. | Circuit breaker module | Data Engineer | R | P1 | Not Started | 4 | 5 | 6 | 6 | 2026-03-30 | 2026-04-03 | IMP-08 | N
IMP-20 | Implementation | Orchestration | 1 | Workflows | Implement controller workflow (fan-out per source/endpoint) | Read registry and create tasks with concurrency limits; support retries and backfill runs. | Controller workflow | Data Engineer | R | P0 | Not Started | 8 | 10 | 6 | 7 | 2026-03-30 | 2026-04-08 | IMP-03,DSN-06,IMP-11 | N
IMP-21 | Implementation | Testing | 1 | Test Harness | Build connector test harness with mock server | Provide mock API server + golden responses; integration tests for templates. | Connector test harness | QA/Test | A | P1 | Not Started | 6 | 8 | 6 | 7 | 2026-03-30 | 2026-04-06 | DSN-18,IMP-05 | N
IMP-37 | Implementation | Compute | 1 | Compute Policies | Implement cluster/job compute policies | Configure cluster policies, autoscaling constraints, tagging for cost attribution. | Compute policies enforced | DevOps/Platform Eng | R | P1 | Not Started | 4 | 5 | 7 | 7 | 2026-04-06 | 2026-04-10 | DSN-16 | N
IMP-57 | Implementation | MVP | 1 | Engine MVP | MVP engine end-to-end demo (2 sources) | Demonstrate config-driven ingestion for 2 sources with checkpoints, Bronze writes, metrics, and reruns. | MVP demo evidence | Data Engineer | R | P0 | Not Started | 2 | 2 | 8 | 8 | 2026-04-13 | 2026-04-14 | IMP-05,IMP-10,IMP-14,IMP-23 | Y
IMP-15 | Implementation | Security | 2 | Secrets & Identity | Integrate external secret manager with Databricks secret scopes | Configure secret scopes, references, naming conventions across dev/stage/prod. | Secret manager integration | Security/Identity Eng | A | P0 | Not Started | 6 | 7 | 4 | 4 | 2026-03-16 | 2026-03-22 | DSN-07 | N
IMP-18 | Implementation | DevSecOps | 2 | CI/CD | Implement CI pipeline (tests, lint, packaging) | Build pipeline running unit tests, static checks, dependency scanning, package artifacts. | CI pipeline live | DevOps/Platform Eng | R | P0 | Not Started | 7 | 9 | 4 | 5 | 2026-03-16 | 2026-03-24 | DSN-14,DSN-18 | N
IMP-16 | Implementation | Security | 2 | Secrets & Identity | Implement auth handlers (OAuth2/API key) in runtime | Add auth middleware, token caching, refresh scheduling and safe logging (no secrets). | Auth modules implemented | Data Engineer | R | P0 | Not Started | 6 | 7 | 5 | 5 | 2026-03-23 | 2026-03-29 | IMP-16,IMP-07 | N
IMP-17 | Implementation | Security | 2 | Secrets & Identity | Implement service principals for jobs + UC permissions | Create SPNs, assign policies, grant UC permissions, attach to workflows. | Service principals in place | Security/Identity Eng | A | P0 | Not Started | 5 | 6 | 5 | 5 | 2026-03-23 | 2026-03-28 | SOP-09,PLY-11 | N
IMP-19 | Implementation | DevSecOps | 2 | CD/IaC | Implement IaC for Jobs/Workflows/Permissions | Terraform modules for jobs, clusters, permissions, secret scope references, env configs. | IaC baseline | DevOps/Platform Eng | R | P1 | Not Started | 8 | 10 | 6 | 7 | 2026-03-30 | 2026-04-08 | IMP-19,DSN-14 | N
IMP-34 | Implementation | Governance | 2 | Permissions | Implement UC permission templates (by classification/tier) | Create groups and grants for Bronze/metrics/audit; map to data classification. | UC permissions applied | Security/Identity Eng | A | P0 | Not Started | 5 | 6 | 7 | 7 | 2026-04-06 | 2026-04-11 | PLY-05,PLY-11,IMP-17 | N
IMP-56 | Implementation | Security | 2 | Reviews | Security design review & signoff | Review secrets, identities, access control, logging and rotation; address findings. | Security review signoff | Security/Identity Eng | A | P0 | Not Started | 3 | 3 | 7 | 7 | 2026-04-06 | 2026-04-08 | IMP-16,IMP-17,PLY-16 | Y
IMP-33 | Implementation | Governance | 2 | Documentation | Publish Policies & Processes set (approved) | Create documents, run approvals, publish in central repository with versioning. | Approved governance docs | Product Owner | A | P0 | Not Started | 6 | 8 | 8 | 9 | 2026-04-13 | 2026-04-20 | PLY-01,PLY-02,PLY-03,PLY-07,PRC-01 | N
IMP-36 | Implementation | DevSecOps | 2 | CD | Implement CD pipeline (deploy dev/stage/prod with gates) | Automate deployments of jobs, libraries and configs with approvals and smoke tests. | CD pipeline live | DevOps/Platform Eng | R | P0 | Not Started | 8 | 10 | 8 |  |  |  | IMP-20,IMP-19 | N
IMP-32 | Implementation | Governance | 2 | Documentation | Draft Operations Handbook v1 | Create handbook: architecture, SLOs, dashboards, alerts, runbooks, escalation, release process. | Ops handbook v1 | SRE/Operations | A | P1 | Not Started | 5 | 6 | 9 |  |  |  | DSN-15,IMP-24 | N
IMP-38 | Implementation | Security | 2 | Monitoring | Implement security audit logs and monitoring | Capture permission changes, secret scope changes, deploy events; integrate with SIEM if applicable. | Security monitoring live | Security/Identity Eng | A | P1 | Not Started | 5 | 6 | 9 |  |  |  | PLY-16,IMP-32 | N
IMP-35 | Implementation | Governance | 2 | Retention | Implement retention purge jobs | Scheduled jobs to enforce Bronze/log/DLQ retention with audit evidence. | Retention jobs live | Data Engineer | R | P1 | Not Started | 4 | 5 | 11 |  |  |  | DSN-17,PLY-06 | N
IMP-22 | Implementation | Observability | 3 | Metrics | Implement metrics tables and logging | Create ingestion.runs, ingestion.metrics, ingestion.errors population and standardized logging. | Metrics+logs implemented | Data Engineer | R | P0 | Not Started | 6 | 8 | 6 |  |  |  | DSN-08,IMP-03 | N
IMP-61 | Implementation | Reliability | 3 | Idempotency | Implement deduplication/idempotency strategy | Implement payload hashing/record keys and merge strategy where needed; document per-source approach. | Idempotency implemented | Data Engineer | R | P0 | Not Started | 4 | 6 | 6 |  |  |  | IMP-14,IMP-10 | N
IMP-23 | Implementation | Observability | 3 | Dashboards | Build Ops dashboard (runs, failures, lag, DLQ) | Create dashboards in chosen tooling (DBSQL/Lakeview/etc.) for ops use. | Ops dashboard v1 | SRE/Operations | A | P0 | Not Started | 5 | 6 | 8 |  |  |  | IMP-23 | N
IMP-26 | Implementation | Data Quality | 3 | DQ Framework | Implement DQ rule engine (config-driven) | Implement rules evaluation and results table, enforcement modes (warn/quarantine/fail). | DQ engine v1 | Data Engineer | R | P1 | Not Started | 7 | 9 | 8 |  |  |  | DSN-10,IMP-03 | N
IMP-62 | Implementation | Operations | 3 | Tickets | Set up ticket queues and templates (Incidents/Requests) | Create Jira/ADO templates for incidents, backfill requests, onboarding requests and access reviews. | Ticket templates live | Product Owner | A | P2 | Not Started | 2 | 2 | 8 |  |  |  | PLY-02,PRC-02,PRC-06 | N
IMP-24 | Implementation | Observability | 3 | Dashboards | Build Exec dashboard (SLO compliance, top offenders) | High level view; includes tiering filters and trends. | Exec dashboard v1 | Product Owner | A | P1 | Not Started | 4 | 5 | 9 |  |  |  | IMP-24,PLY-10 | N
IMP-25 | Implementation | Alerting | 3 | Alerts | Implement alert rules + routing | Create alert rules mapped to P0-P3; configure routing to on-call and owners. | Alerts live | SRE/Operations | A | P0 | Not Started | 6 | 7 | 9 |  |  |  | DSN-09,IMP-23 | N
IMP-27 | Implementation | DLQ/Replay | 3 | DLQ | Implement DLQ tables + writer | Write failing records and context to DLQ; link to runs/errors; retention. | DLQ implemented | Data Engineer | R | P1 | Not Started | 5 | 6 | 9 |  |  |  | DSN-11,IMP-27 | N
IMP-29 | Implementation | Schema Evolution | 3 | Schema Drift | Implement schema drift detection | Detect schema changes (add/remove/type), record versions, quarantine breaking changes. | Schema drift detector v1 | Data Engineer | R | P1 | Not Started | 6 | 8 | 9 |  |  |  | DSN-12,IMP-14 | N
IMP-30 | Implementation | Lineage | 3 | Audit & Lineage | Implement audit logging tables and events | Populate audit events: deploy versions, config versions, secret references, table writes. | Audit logging v1 | Data Engineer | R | P1 | Not Started | 5 | 6 | 10 |  |  |  | DSN-13,IMP-23 | N
IMP-58 | Implementation | Observability | 3 | Go-live | Observability framework go-live (dashboards + alerts) | Go-live with dashboards, alerts, routing and runbooks; validate alert storms suppressed. | Observability live | SRE/Operations | A | P0 | Not Started | 2 | 2 | 10 |  |  |  | IMP-24,IMP-26,SOP-16 | Y
IMP-31 | Implementation | Lineage | 3 | Audit & Lineage | Enable UC lineage + validate critical flows | Ensure pipelines register lineage; validate on key bronze tables; document limitations. | Lineage enabled + validated | Data Platform Architect | A | P2 | Not Started | 3 | 4 | 11 |  |  |  | IMP-32 | N
IMP-60 | Implementation | Schema Evolution | 3 | Policy Enforcement | Implement schema quarantine pipeline | When breaking changes detected, quarantine affected sources/endpoints and notify owners; allow override approvals. | Schema quarantine workflow | Data Engineer | R | P1 | Not Started | 4 | 5 | 11 |  |  |  | IMP-31,IMP-26 | N
IMP-59 | Implementation | Governance | 4 | Onboarding | Implement source intake form (template + storage) | Create standardized intake form (Confluence/Sharepoint) and storage; link into onboarding process. | Intake form published | Product Owner | A | P1 | Not Started | 2 | 2 | 7 |  |  |  | PRC-06,SOP-21 | N
IMP-39 | Implementation | Pilot | 4 | Pilot Onboarding | Pilot onboarding - Source 1–3 (mixed auth) | Onboard first set of sources covering API key and OAuth2 patterns; verify SLOs and runbooks. | 3 pilot sources in prod | Data Engineer | R | P0 | Not Started | 10 | 10 | 9 |  |  |  | IMP-21,IMP-07,IMP-23,IMP-24 | Y
IMP-28 | Implementation | DLQ/Replay | 4 | Replay | Implement replay tooling (by run_id/window/DLQ) | Jobs/notebooks for safe replay; ensure idempotency; capture evidence. | Replay tooling | Data Engineer | R | P1 | Not Started | 5 | 6 | 10 |  |  |  | IMP-28,IMP-10 | N
IMP-40 | Implementation | Pilot | 4 | Pilot Onboarding | Pilot onboarding - Source 4–8 (pagination + rate limits) | Onboard sources with complex pagination and strict rate limits; tune throttling; validate alerts. | 8 pilot sources total | Data Engineer | R | P0 | Not Started | 12 | 12 | 10 |  |  |  | IMP-42,IMP-26 | N
IMP-42 | Implementation | Testing | 4 | Contract Tests | Implement contract tests for pilot APIs | Create schema/response contract tests for pilot sources; schedule daily checks in non-prod. | Pilot contract tests | QA/Test | A | P1 | Not Started | 6 | 8 | 10 |  |  |  | IMP-22,IMP-43 | N
IMP-41 | Implementation | Pilot | 4 | Pilot Validation | Pilot stabilization period (2 weeks) | Operate pilot with on-call processes; fix defects; finalize templates and thresholds. | Pilot stability report | SRE/Operations | A | P0 | Not Started | 8 | 10 | 11 |  |  |  | IMP-43 | Y
IMP-45 | Implementation | Scale-out | 5 | Wave 1 | Wave 1 onboarding (20 APIs) | Onboard next 20 standard-pattern APIs using templates; measure throughput and incident rate. | 20 new APIs live | Data Engineer | R | P1 | Not Started | 20 | 10 | 14 |  |  |  | IMP-44,DSN-19 | N
IMP-46 | Implementation | Scale-out | 5 | Wave 1 | Wave 1 retrospectives + template improvements | Review onboarding pain points; improve templates, docs, dashboards; tune defaults. | Improvement backlog + releases | Data Platform Architect | A | P2 | Not Started | 5 | 5 | 16 |  |  |  | IMP-49 | N
IMP-50 | Implementation | Scale-out | 5 | Automation | Build bulk onboarding helper (config generator) | Tooling (notebook/UI) to generate validated configs and vendor profiles from intake forms. | Bulk onboarding tool | Data Engineer | R | P2 | Not Started | 8 | 10 | 16 |  |  |  | DSN-19,IMP-35 | N
IMP-47 | Implementation | Scale-out | 5 | Wave 2 | Wave 2 onboarding (30 APIs) | Onboard 30 APIs (mixed complexity). Ensure owners assigned and SLOs configured. | 30 more APIs live | Data Engineer | R | P1 | Not Started | 30 | 15 | 17 |  |  |  | IMP-50 | N
IMP-49 | Implementation | Scale-out | 5 | Operations | Implement cost attribution dashboard (showback) | Dashboard compute/storage per source/vendor; identify top spenders; feed to tuning. | Cost dashboard | DevOps/Platform Eng | A | P2 | Not Started | 6 | 7 | 18 |  |  |  | DSN-20,IMP-23 | N
IMP-51 | Implementation | Scale-out | 5 | Quality | Enhance anomaly detection on volume/freshness | Add baseline anomaly detection (counts/lag) and alert on deviations; tune thresholds. | Anomaly detection v1 | SRE/Operations | A | P2 | Not Started | 6 | 8 | 19 |  |  |  | IMP-26 | N
IMP-48 | Implementation | Scale-out | 5 | Wave 3 | Wave 3 onboarding (40 APIs) | Onboard 40 APIs; include higher complexity; expand vendor profiles; enforce gates. | 40 more APIs live | Data Engineer | R | P2 | Not Started | 40 | 20 | 20 |  |  |  | IMP-51 | N
IMP-63 | Implementation | Governance | 5 | Decommission | Tag and track deprecated/unused sources | Add registry fields and reports for unused sources; prepare for decommission wave. | Deprecated sources report | Data Engineer | R | P3 | Not Started | 2 | 3 | 21 |  |  |  | IMP-03 | N
IMP-52 | Implementation | Scale-out | 5 | Governance | Implement decommission workflow automation | Automate disabling schedules, archiving configs, and updating registry status. | Decommission automation | DevOps/Platform Eng | R | P3 | Not Started | 4 | 5 | 22 |  |  |  | PRC-12 | N
IMP-43 | Implementation | Operations | 6 | ORR | Execute Operational Readiness Review (ORR) | Run ORR checklist, ensure runbooks, SLOs, alerts, permissions, DR tested; obtain signoff. | ORR signoff | SRE/Operations | A | P0 | Not Started | 5 | 5 | 13 |  |  |  | PRC-10,IMP-44,IMP-34 | Y
IMP-44 | Implementation | Operations | 6 | Game Days | Conduct game days (token expiry, vendor outage, schema break) | Simulate failures, validate alert routing, runbooks, and recovery procedures; capture actions. | Game day evidence pack | SRE/Operations | A | P1 | Not Started | 5 | 6 | 13 |  |  |  | PRC-11,IMP-46 | N
IMP-53 | Implementation | Operations | 6 | Handover | Ops training + handover to run team | Training sessions for on-call, walk through dashboards/runbooks, define steady-state rituals. | Handover complete | SRE/Operations | A | P1 | Not Started | 4 | 4 | 14 |  |  |  | IMP-46 | N
IMP-54 | Implementation | Operations | 6 | Documentation | Finalize operations handbook and runbook set | Incorporate lessons from pilot and game days; publish final versions; set review cadence. | Ops docs v1.0 | SRE/Operations | A | P1 | Not Started | 4 | 5 | 14 |  |  |  | IMP-34,IMP-47 | N
PLY-01 | Policy | Governance | 0 | Program Governance | Define program success criteria & scope | Define what 'productionized' means (SLOs, security, audit, runbooks), confirm scope across 100s of APIs. | Productionization definition + success metrics | Product Owner | A | P1 | Not Started | 3 | 3 | 1 |  |  |  |  | N
PLY-02 | Policy | Operations | 0 | Incident Management | Define defect prioritization & incident severity (P0–P3) | Create severity definitions, response targets, escalation triggers and mapping to alerts. | P0–P3 severity policy + response SLAs | SRE/Operations | A | P0 | Not Started | 4 | 4 | 1 |  |  |  | PLY-01 | N
PLY-03 | Policy | Security | 2 | Secrets & Identity | Service account and credential policy | Define rules: no personal tokens in prod, service principals, least privilege, ownership and audit. | Service account policy (Databricks + vendor) | Security/Identity Eng | A | P0 | Not Started | 4 | 4 | 2 |  |  |  | PLY-01 | N
PLY-04 | Policy | Security | 2 | Secrets & Identity | Credential rotation policy | Define rotation frequency, emergency rotation, break-glass access, audit requirements. | Credential rotation policy | Security/Identity Eng | A | P0 | Not Started | 3 | 3 | 2 |  |  |  | PLY-03 | N
PLY-05 | Policy | Governance | 2 | Data Governance | Data classification policy for ingested data | Define classification levels and handling rules for Bronze payloads (PII/PHI), masking/encryption, access rules. | Data classification policy | Security/Identity Eng | C | P0 | Not Started | 5 | 5 | 3 |  |  |  | PLY-01 | N
PLY-06 | Policy | Governance | 2 | Retention | Retention & purge policy (Bronze, logs, audit) | Define retention periods for raw payloads, metrics, audit logs, DLQ, and purge mechanisms. | Retention policy + purge requirements | Data Platform Architect | A | P1 | Not Started | 4 | 4 | 3 |  |  |  | PLY-05 | N
PLY-07 | Policy | DevSecOps | 2 | Change Management | Release & change management policy | Define promotion gates, approvals, freeze windows, emergency hotfix rules, rollback expectations. | Change/release policy | Release Manager | A | P0 | Not Started | 4 | 4 | 3 |  |  |  | PLY-01 | N
PLY-08 | Policy | DevSecOps | 2 | SDLC | Branching and versioning policy | Define branching strategy, artifact versioning, semantic version rules for connectors/runtime. | SDLC versioning policy | DevOps/Platform Eng | A | P1 | Not Started | 3 | 3 | 3 |  |  |  | PLY-07 | N
PLY-11 | Policy | Governance | 2 | Access Control | Access control policy (Unity Catalog) | Define who can read/write Bronze, how domain teams access data, access review cadence. | UC access control policy | Security/Identity Eng | A | P0 | Not Started | 4 | 4 | 4 |  |  |  | PLY-05 | N
PLY-15 | Policy | Security | 2 | Security Monitoring | Security logging and audit evidence policy | Define required audit events (deployments, secret references, permission changes) and evidence retention. | Security audit logging policy | Security/Identity Eng | A | P0 | Not Started | 4 | 4 | 4 |  |  |  | PLY-03,PLY-07 | N
PLY-10 | Policy | Operations | 3 | SLO/SLA | SLO policy (availability, freshness, latency) | Define SLO targets per tier (Tier-0/1/2), measurement method, and breach handling. | SLO policy + tier definitions | Product Owner | A | P1 | Not Started | 4 | 4 | 4 |  |  |  | PLY-01 | N
PLY-09 | Policy | Operations | 3 | Observability | Alerting policy and routing standards | Define paging vs ticket alerts, quiet hours, dedupe/suppression, escalation paths (platform vs domain owners). | Alerting & routing policy | SRE/Operations | A | P0 | Not Started | 4 | 4 | 5 |  |  |  | PLY-02 | N
PLY-13 | Policy | Governance | 4 | Source Onboarding | Source onboarding acceptance criteria policy | Define mandatory metadata: owner, SLA, classification, auth method, rate limits, sample payload, DQ rules. | Onboarding gate policy | Data Platform Architect | A | P1 | Not Started | 3 | 3 | 7 |  |  |  | PLY-05,PLY-10 | N
PLY-12 | Policy | Governance | 5 | Vendor Management | Vendor escalation policy | Define when/how to escalate to API vendors; required evidence and communication templates. | Vendor escalation policy + templates | SRE/Operations | A | P2 | Not Started | 2 | 2 | 10 |  |  |  | PLY-02 | N
PLY-14 | Policy | Governance | 5 | Decommission | Source decommission policy | Define how to retire sources, archive configs, retention handling, and stakeholder notifications. | Decommission policy | Product Owner | A | P3 | Not Started | 2 | 2 | 14 |  |  |  | PLY-14 | N
SOP-09 | Procedure | Security | 2 | SOP | SOP: Create and configure service principal for jobs | Procedure to create SPN, assign UC permissions, attach to jobs, validate least privilege. | Service principal SOP | Security/Identity Eng | R | P0 | Not Started | 3 | 3 | 6 |  |  |  | PLY-03 | N
SOP-10 | Procedure | Security | 2 | SOP | SOP: Credential rotation execution | Step-by-step rotation execution including smoke tests, rollback, and evidence capture. | Rotation SOP | Security/Identity Eng | R | P0 | Not Started | 3 | 3 | 7 |  |  |  | PRC-04 | N
SOP-11 | Procedure | DevSecOps | 2 | SOP | SOP: Production deployment (standard release) | Steps for release manager and approvers to promote artifacts, verify and rollback. | Deployment SOP | Release Manager | R | P0 | Not Started | 3 | 3 | 8 |  |  |  | PRC-05 | N
SOP-12 | Procedure | DevSecOps | 2 | SOP | SOP: Emergency hotfix | Steps for urgent changes with expedited approvals and post-facto review requirements. | Hotfix SOP | Release Manager | R | P0 | Not Started | 2 | 2 | 9 |  |  |  | PLY-07 | N
SOP-13 | Procedure | Governance | 2 | SOP | SOP: Quarterly access review execution | How to export permissions, review against policy, collect signoffs, remediate and record evidence. | Access review SOP | Security/Identity Eng | R | P1 | Not Started | 2 | 2 | 11 |  |  |  | PRC-07 | N
SOP-01 | Procedure | Operations | 3 | Runbooks | Runbook template + standard structure | Create runbook template including symptoms, diagnostics, actions, rollback, escalation, and evidence capture. | Runbook template | SRE/Operations | A | P1 | Not Started | 2 | 2 | 6 |  |  |  | PRC-02 | N
SOP-02 | Procedure | Operations | 3 | Runbooks | Runbook: Authentication failures (401/403) | Step-by-step for diagnosing credential issues, secret references, token refresh, and vendor checks. | Auth failure runbook | SRE/Operations | R | P0 | Not Started | 2 | 2 | 7 |  |  |  | SOP-01,PRC-03 | N
SOP-03 | Procedure | Operations | 3 | Runbooks | Runbook: Rate limiting / 429 handling | Steps to confirm rate-limit cause, adjust throttles, reschedule, and contact vendor if needed. | 429 runbook | SRE/Operations | R | P1 | Not Started | 2 | 2 | 7 |  |  |  | SOP-01 | N
SOP-04 | Procedure | Operations | 3 | Runbooks | Runbook: Vendor outage / elevated 5xx | Steps to validate vendor outage, mitigate via retries/circuit breaker, and communicate status. | 5xx outage runbook | SRE/Operations | R | P1 | Not Started | 2 | 2 | 7 |  |  |  | SOP-01 | N
SOP-05 | Procedure | Operations | 3 | Runbooks | Runbook: Schema drift detected | Diagnose schema changes, identify breaking vs additive, quarantine rules, and escalation to owners. | Schema drift runbook | Data Engineer | R | P1 | Not Started | 2 | 2 | 8 |  |  |  | SOP-01 | N
SOP-06 | Procedure | Operations | 3 | Runbooks | Runbook: Bronze write failures (storage/permissions) | Check UC permissions, storage mount, Delta transaction errors, and recovery steps. | Bronze write failure runbook | SRE/Operations | R | P0 | Not Started | 2 | 2 | 8 |  |  |  | SOP-01 | N
SOP-19 | Procedure | Operations | 3 | Procedure | Procedure: Classify an ingestion failure (taxonomy) | Map common errors to error types, severity, and routing; ensure consistent categorization in errors table. | Error taxonomy procedure | SRE/Operations | R | P1 | Not Started | 2 | 2 | 8 |  |  |  | PLY-02 | N
SOP-07 | Procedure | Operations | 3 | Runbooks | Runbook: DLQ growth / parse failures | Identify root cause, isolate sources/endpoints, replay strategy and validation steps. | DLQ growth runbook | Data Engineer | R | P1 | Not Started | 2 | 2 | 9 |  |  |  | SOP-01 | N
SOP-21 | Procedure | Operations | 3 | Runbooks | Runbook: Config validation/publish failure | Steps to diagnose CI config validation failures and registry publish issues. | Config publish runbook | DevOps/Platform Eng | R | P1 | Not Started | 2 | 2 | 9 |  |  |  | SOP-01 | N
SOP-22 | Procedure | Operations | 3 | Runbooks | Runbook: Stuck jobs / orchestration failures | Diagnose workflow/task failures, cluster issues, concurrency limits. | Orchestration runbook | SRE/Operations | R | P1 | Not Started | 2 | 2 | 9 |  |  |  | SOP-01 | N
SOP-15 | Procedure | Operations | 3 | SOP | SOP: Alert tuning and suppression | Procedure to adjust thresholds, implement dedupe, suppression windows, and track changes. | Alert tuning SOP | SRE/Operations | R | P2 | Not Started | 2 | 2 | 10 |  |  |  | PLY-09 | N
SOP-23 | Procedure | Operations | 3 | Runbooks | Runbook: Data freshness lag breach | Diagnose lag, check schedule, rate limits, upstream delays, and mitigation. | Freshness lag runbook | SRE/Operations | R | P1 | Not Started | 2 | 2 | 10 |  |  |  | SOP-01 | N
SOP-20 | Procedure | Governance | 4 | Procedure | Procedure: Source intake form completion | Detailed instructions for requestors to complete the intake form (required fields and examples). | Intake form instructions | Product Owner | R | P2 | Not Started | 1 | 1 | 7 |  |  |  | PRC-06 | N
SOP-08 | Procedure | Operations | 4 | SOP | SOP: Source onboarding checklist (operator view) | Step-by-step to onboard a source using templates, configs, secret references and enabling schedules. | Onboarding SOP | Data Engineer | R | P1 | Not Started | 3 | 3 | 9 |  |  |  | PRC-06 | N
SOP-14 | Procedure | Operations | 4 | SOP | SOP: Backfill execution | How to run approved backfills, manage compute, validate row counts and close request with evidence. | Backfill SOP | Data Engineer | R | P2 | Not Started | 2 | 2 | 10 |  |  |  | PRC-08 | N
SOP-24 | Procedure | Operations | 5 | SOP | SOP: Retention purge job execution | How to run/verify purge jobs, validate deletions, and capture evidence. | Purge SOP | SRE/Operations | R | P2 | Not Started | 2 | 2 | 12 |  |  |  | SOP-01 | N
SOP-25 | Procedure | Operations | 5 | SOP | SOP: Compute cost anomaly investigation | Procedure to investigate cost spikes, identify offending sources, and tune schedules/throttles. | Cost anomaly SOP | SRE/Operations | R | P2 | Not Started | 2 | 2 | 13 |  |  |  | SOP-01 | N
SOP-18 | Procedure | Operations | 5 | SOP | SOP: Source decommission | How to disable pipelines, archive configs, set retention, notify stakeholders, and update registry. | Decommission SOP | Data Engineer | R | P3 | Not Started | 2 | 2 | 15 |  |  |  | PRC-12 | N
SOP-16 | Procedure | Operations | 6 | SOP | SOP: ORR execution and signoff | Step-by-step to run ORR checklist, gather evidence, and secure signoffs. | ORR SOP | SRE/Operations | R | P0 | Not Started | 2 | 2 | 12 |  |  |  | PRC-10 | N
SOP-17 | Procedure | Operations | 6 | SOP | SOP: Post-incident review (PIR) / postmortem | How to conduct PIRs, write report, track action items and update runbooks/policies. | PIR template + SOP | SRE/Operations | R | P1 | Not Started | 2 | 2 | 12 |  |  |  | PRC-02 | N
PRC-01 | Process | Governance | 0 | Program Governance | Establish RACI & operating model | Define responsibilities for platform vs domain teams: onboarding, incident response, releases, data ownership. | RACI matrix + operating model | Product Owner | A | P1 | Not Started | 3 | 3 | 1 |  |  |  | PLY-01 | N
PRC-15 | Process | Governance | 0 | Planning | API source tiering and onboarding wave planning | Segment sources by criticality/complexity; plan waves and capacity model. | Tiering + onboarding waves plan | Data Platform Architect | A | P1 | Not Started | 4 | 4 | 2 |  |  |  | PLY-01 | N
PRC-13 | Process | DevSecOps | 2 | Config Management | Config lifecycle process (Git→validate→publish) | Define how source configs are authored, validated, versioned, and published to registry tables. | Config lifecycle process | DevOps/Platform Eng | A | P1 | Not Started | 4 | 4 | 4 |  |  |  | PLY-08 | N
PRC-04 | Process | Security | 2 | Credential Rotation | Credential rotation workflow | Define rotation steps across vault, Databricks scopes, smoke tests, rollback, evidence capture. | Rotation process flow | Security/Identity Eng | A | P0 | Not Started | 3 | 3 | 6 |  |  |  | PLY-04 | N
PRC-05 | Process | DevSecOps | 2 | Release Management | Promotion workflow (Dev→Stage→Prod) | Define CI/CD stages, approvals, automated checks, deployment verification and rollback. | Release promotion workflow | Release Manager | A | P0 | Not Started | 4 | 4 | 6 |  |  |  | PLY-07 | N
PRC-02 | Process | Operations | 3 | Incident Management | Incident triage workflow | Define triage steps, ticket creation, severity assignment, communication, escalation and closure. | Incident triage process flow | SRE/Operations | A | P0 | Not Started | 3 | 3 | 5 |  |  |  | PLY-02 | N
PRC-03 | Process | Operations | 3 | Alerting | Alert intake & response workflow | Define who gets alerted, how to acknowledge, response time targets, and handoff to domain owners. | Alert response workflow | SRE/Operations | A | P0 | Not Started | 3 | 3 | 5 |  |  |  | PLY-09,PRC-02 | N
PRC-14 | Process | Operations | 3 | Communications | Status communications & stakeholder updates process | Define comms channels, frequency, templates for incidents and planned changes. | Comms process + templates | Product Owner | A | P2 | Not Started | 2 | 2 | 8 |  |  |  | PRC-02 | N
PRC-06 | Process | Governance | 4 | Source Onboarding | Source onboarding end-to-end process | Intake → validation → secrets provision → config publish → test → prod enablement → handover. | Onboarding process + checklist | Data Platform Architect | A | P1 | Not Started | 5 | 5 | 7 |  |  |  | PLY-14,PRC-01 | N
PRC-08 | Process | Operations | 4 | Backfill | Backfill request and execution process | Define intake, approvals, compute planning, execution, validation and cost tracking for backfills. | Backfill process | Data Engineer | R | P2 | Not Started | 3 | 3 | 9 |  |  |  | PLY-07,PRC-05 | N
PRC-09 | Process | Operations | 4 | Replay/DLQ | DLQ reprocessing process | Define criteria for reprocessing DLQ, approvals, replay execution, and verification steps. | DLQ replay process | SRE/Operations | R | P1 | Not Started | 3 | 3 | 9 |  |  |  | PRC-02 | N
PRC-07 | Process | Governance | 5 | Access Review | Periodic access review process | Define cadence (e.g., quarterly), review steps, evidence capture, and remediation workflow. | Access review process | Security/Identity Eng | A | P1 | Not Started | 3 | 3 | 10 |  |  |  | PLY-11 | N
PRC-12 | Process | Governance | 5 | Decommission | Source decommission workflow | Define steps to disable schedules, archive configs, retain data, and notify consumers. | Decommission workflow | Product Owner | A | P3 | Not Started | 2 | 2 | 14 |  |  |  | PLY-15 | N
PRC-10 | Process | Operations | 6 | Operational Readiness | Operational Readiness Review (ORR) process | Define ORR checklist, gates, evidence requirements and signoff. | ORR process & checklist | SRE/Operations | A | P0 | Not Started | 4 | 4 | 11 |  |  |  | PLY-02,PLY-09,PLY-07 | N
PRC-11 | Process | Operations | 6 | Game Days | Game day & DR drill process | Define how to simulate outages (vendor outage, token expiry, schema break), roles and success criteria. | Game day process | SRE/Operations | A | P1 | Not Started | 3 | 3 | 12 |  |  |  | PRC-10 | N
Formulas:
Start Date = Inputs!$B3+([Start Week]-1)*Inputs!$B4
End Date = [Start Date]+[Duration (days)]-1

## Policy
Policy – Work Breakdown Structure (WBS)
Update Status and Notes/Evidence Link during execution. Dates auto-calc from Inputs.
Task ID | Category | Workstream | Phase | Module | Task Name | Task Description | Deliverable/Artifact | Owner Role | RACI | Priority | Status | Est Effort (Person-days) | Duration (days) | Start Week | End Week | Start Date | End Date | Dependencies | Milestone (Y/N) | Notes/Evidence Link
PLY-01 | Policy | Governance | 0 | Program Governance | Define program success criteria & scope | Define what 'productionized' means (SLOs, security, audit, runbooks), confirm scope across 100s of APIs. | Productionization definition + success metrics | Product Owner | A | P1 | Not Started | 3 | 3 | 1 | 1 | 2026-02-23 | 2026-02-25 |  | N
PLY-02 | Policy | Operations | 0 | Incident Management | Define defect prioritization & incident severity (P0–P3) | Create severity definitions, response targets, escalation triggers and mapping to alerts. | P0–P3 severity policy + response SLAs | SRE/Operations | A | P0 | Not Started | 4 | 4 | 1 | 1 | 2026-02-23 | 2026-02-26 | PLY-01 | N
PLY-03 | Policy | Security | 2 | Secrets & Identity | Service account and credential policy | Define rules: no personal tokens in prod, service principals, least privilege, ownership and audit. | Service account policy (Databricks + vendor) | Security/Identity Eng | A | P0 | Not Started | 4 | 4 | 2 | 2 | 2026-03-02 | 2026-03-05 | PLY-01 | N
PLY-04 | Policy | Security | 2 | Secrets & Identity | Credential rotation policy | Define rotation frequency, emergency rotation, break-glass access, audit requirements. | Credential rotation policy | Security/Identity Eng | A | P0 | Not Started | 3 | 3 | 2 | 2 | 2026-03-02 | 2026-03-04 | PLY-03 | N
PLY-05 | Policy | Governance | 2 | Data Governance | Data classification policy for ingested data | Define classification levels and handling rules for Bronze payloads (PII/PHI), masking/encryption, access rules. | Data classification policy | Security/Identity Eng | C | P0 | Not Started | 5 | 5 | 3 | 3 | 2026-03-09 | 2026-03-13 | PLY-01 | N
PLY-06 | Policy | Governance | 2 | Retention | Retention & purge policy (Bronze, logs, audit) | Define retention periods for raw payloads, metrics, audit logs, DLQ, and purge mechanisms. | Retention policy + purge requirements | Data Platform Architect | A | P1 | Not Started | 4 | 4 | 3 | 3 | 2026-03-09 | 2026-03-12 | PLY-05 | N
PLY-07 | Policy | DevSecOps | 2 | Change Management | Release & change management policy | Define promotion gates, approvals, freeze windows, emergency hotfix rules, rollback expectations. | Change/release policy | Release Manager | A | P0 | Not Started | 4 | 4 | 3 | 3 | 2026-03-09 | 2026-03-12 | PLY-01 | N
PLY-08 | Policy | DevSecOps | 2 | SDLC | Branching and versioning policy | Define branching strategy, artifact versioning, semantic version rules for connectors/runtime. | SDLC versioning policy | DevOps/Platform Eng | A | P1 | Not Started | 3 | 3 | 3 | 3 | 2026-03-09 | 2026-03-11 | PLY-07 | N
PLY-11 | Policy | Governance | 2 | Access Control | Access control policy (Unity Catalog) | Define who can read/write Bronze, how domain teams access data, access review cadence. | UC access control policy | Security/Identity Eng | A | P0 | Not Started | 4 | 4 | 4 | 4 | 2026-03-16 | 2026-03-19 | PLY-05 | N
PLY-15 | Policy | Security | 2 | Security Monitoring | Security logging and audit evidence policy | Define required audit events (deployments, secret references, permission changes) and evidence retention. | Security audit logging policy | Security/Identity Eng | A | P0 | Not Started | 4 | 4 | 4 | 4 | 2026-03-16 | 2026-03-19 | PLY-03,PLY-07 | N
PLY-10 | Policy | Operations | 3 | SLO/SLA | SLO policy (availability, freshness, latency) | Define SLO targets per tier (Tier-0/1/2), measurement method, and breach handling. | SLO policy + tier definitions | Product Owner | A | P1 | Not Started | 4 | 4 | 4 | 4 | 2026-03-16 | 2026-03-19 | PLY-01 | N
PLY-09 | Policy | Operations | 3 | Observability | Alerting policy and routing standards | Define paging vs ticket alerts, quiet hours, dedupe/suppression, escalation paths (platform vs domain owners). | Alerting & routing policy | SRE/Operations | A | P0 | Not Started | 4 | 4 | 5 | 5 | 2026-03-23 | 2026-03-26 | PLY-02 | N
PLY-13 | Policy | Governance | 4 | Source Onboarding | Source onboarding acceptance criteria policy | Define mandatory metadata: owner, SLA, classification, auth method, rate limits, sample payload, DQ rules. | Onboarding gate policy | Data Platform Architect | A | P1 | Not Started | 3 | 3 | 7 | 7 | 2026-04-06 | 2026-04-08 | PLY-05,PLY-10 | N
PLY-12 | Policy | Governance | 5 | Vendor Management | Vendor escalation policy | Define when/how to escalate to API vendors; required evidence and communication templates. | Vendor escalation policy + templates | SRE/Operations | A | P2 | Not Started | 2 | 2 | 10 | 10 | 2026-04-27 | 2026-04-28 | PLY-02 | N
PLY-14 | Policy | Governance | 5 | Decommission | Source decommission policy | Define how to retire sources, archive configs, retention handling, and stakeholder notifications. | Decommission policy | Product Owner | A | P3 | Not Started | 2 | 2 | 14 | 14 | 2026-05-25 | 2026-05-26 | PLY-14 | N
Formulas:
Start Date = Inputs!$B3+([Start Week]-1)*Inputs!$B4
End Date = [Start Date]+[Duration (days)]-1

## Process
Process – Work Breakdown Structure (WBS)
Update Status and Notes/Evidence Link during execution. Dates auto-calc from Inputs.
Task ID | Category | Workstream | Phase | Module | Task Name | Task Description | Deliverable/Artifact | Owner Role | RACI | Priority | Status | Est Effort (Person-days) | Duration (days) | Start Week | End Week | Start Date | End Date | Dependencies | Milestone (Y/N) | Notes/Evidence Link
PRC-01 | Process | Governance | 0 | Program Governance | Establish RACI & operating model | Define responsibilities for platform vs domain teams: onboarding, incident response, releases, data ownership. | RACI matrix + operating model | Product Owner | A | P1 | Not Started | 3 | 3 | 1 | 1 | 2026-02-23 | 2026-02-25 | PLY-01 | N
PRC-15 | Process | Governance | 0 | Planning | API source tiering and onboarding wave planning | Segment sources by criticality/complexity; plan waves and capacity model. | Tiering + onboarding waves plan | Data Platform Architect | A | P1 | Not Started | 4 | 4 | 2 | 2 | 2026-03-02 | 2026-03-05 | PLY-01 | N
PRC-13 | Process | DevSecOps | 2 | Config Management | Config lifecycle process (Git→validate→publish) | Define how source configs are authored, validated, versioned, and published to registry tables. | Config lifecycle process | DevOps/Platform Eng | A | P1 | Not Started | 4 | 4 | 4 | 4 | 2026-03-16 | 2026-03-19 | PLY-08 | N
PRC-04 | Process | Security | 2 | Credential Rotation | Credential rotation workflow | Define rotation steps across vault, Databricks scopes, smoke tests, rollback, evidence capture. | Rotation process flow | Security/Identity Eng | A | P0 | Not Started | 3 | 3 | 6 | 6 | 2026-03-30 | 2026-04-01 | PLY-04 | N
PRC-05 | Process | DevSecOps | 2 | Release Management | Promotion workflow (Dev→Stage→Prod) | Define CI/CD stages, approvals, automated checks, deployment verification and rollback. | Release promotion workflow | Release Manager | A | P0 | Not Started | 4 | 4 | 6 | 6 | 2026-03-30 | 2026-04-02 | PLY-07 | N
PRC-02 | Process | Operations | 3 | Incident Management | Incident triage workflow | Define triage steps, ticket creation, severity assignment, communication, escalation and closure. | Incident triage process flow | SRE/Operations | A | P0 | Not Started | 3 | 3 | 5 | 5 | 2026-03-23 | 2026-03-25 | PLY-02 | N
PRC-03 | Process | Operations | 3 | Alerting | Alert intake & response workflow | Define who gets alerted, how to acknowledge, response time targets, and handoff to domain owners. | Alert response workflow | SRE/Operations | A | P0 | Not Started | 3 | 3 | 5 | 5 | 2026-03-23 | 2026-03-25 | PLY-09,PRC-02 | N
PRC-14 | Process | Operations | 3 | Communications | Status communications & stakeholder updates process | Define comms channels, frequency, templates for incidents and planned changes. | Comms process + templates | Product Owner | A | P2 | Not Started | 2 | 2 | 8 | 8 | 2026-04-13 | 2026-04-14 | PRC-02 | N
PRC-06 | Process | Governance | 4 | Source Onboarding | Source onboarding end-to-end process | Intake → validation → secrets provision → config publish → test → prod enablement → handover. | Onboarding process + checklist | Data Platform Architect | A | P1 | Not Started | 5 | 5 | 7 | 7 | 2026-04-06 | 2026-04-10 | PLY-14,PRC-01 | N
PRC-08 | Process | Operations | 4 | Backfill | Backfill request and execution process | Define intake, approvals, compute planning, execution, validation and cost tracking for backfills. | Backfill process | Data Engineer | R | P2 | Not Started | 3 | 3 | 9 | 9 | 2026-04-20 | 2026-04-22 | PLY-07,PRC-05 | N
PRC-09 | Process | Operations | 4 | Replay/DLQ | DLQ reprocessing process | Define criteria for reprocessing DLQ, approvals, replay execution, and verification steps. | DLQ replay process | SRE/Operations | R | P1 | Not Started | 3 | 3 | 9 | 9 | 2026-04-20 | 2026-04-22 | PRC-02 | N
PRC-07 | Process | Governance | 5 | Access Review | Periodic access review process | Define cadence (e.g., quarterly), review steps, evidence capture, and remediation workflow. | Access review process | Security/Identity Eng | A | P1 | Not Started | 3 | 3 | 10 | 10 | 2026-04-27 | 2026-04-29 | PLY-11 | N
PRC-12 | Process | Governance | 5 | Decommission | Source decommission workflow | Define steps to disable schedules, archive configs, retain data, and notify consumers. | Decommission workflow | Product Owner | A | P3 | Not Started | 2 | 2 | 14 | 14 | 2026-05-25 | 2026-05-26 | PLY-15 | N
PRC-10 | Process | Operations | 6 | Operational Readiness | Operational Readiness Review (ORR) process | Define ORR checklist, gates, evidence requirements and signoff. | ORR process & checklist | SRE/Operations | A | P0 | Not Started | 4 | 4 | 11 | 11 | 2026-05-04 | 2026-05-07 | PLY-02,PLY-09,PLY-07 | N
PRC-11 | Process | Operations | 6 | Game Days | Game day & DR drill process | Define how to simulate outages (vendor outage, token expiry, schema break), roles and success criteria. | Game day process | SRE/Operations | A | P1 | Not Started | 3 | 3 | 12 | 12 | 2026-05-11 | 2026-05-13 | PRC-10 | N
Formulas:
Start Date = Inputs!$B3+([Start Week]-1)*Inputs!$B4
End Date = [Start Date]+[Duration (days)]-1

## Procedure
Procedure – Work Breakdown Structure (WBS)
Update Status and Notes/Evidence Link during execution. Dates auto-calc from Inputs.
Task ID | Category | Workstream | Phase | Module | Task Name | Task Description | Deliverable/Artifact | Owner Role | RACI | Priority | Status | Est Effort (Person-days) | Duration (days) | Start Week | End Week | Start Date | End Date | Dependencies | Milestone (Y/N) | Notes/Evidence Link
SOP-09 | Procedure | Security | 2 | SOP | SOP: Create and configure service principal for jobs | Procedure to create SPN, assign UC permissions, attach to jobs, validate least privilege. | Service principal SOP | Security/Identity Eng | R | P0 | Not Started | 3 | 3 | 6 | 6 | 2026-03-30 | 2026-04-01 | PLY-03 | N
SOP-10 | Procedure | Security | 2 | SOP | SOP: Credential rotation execution | Step-by-step rotation execution including smoke tests, rollback, and evidence capture. | Rotation SOP | Security/Identity Eng | R | P0 | Not Started | 3 | 3 | 7 | 7 | 2026-04-06 | 2026-04-08 | PRC-04 | N
SOP-11 | Procedure | DevSecOps | 2 | SOP | SOP: Production deployment (standard release) | Steps for release manager and approvers to promote artifacts, verify and rollback. | Deployment SOP | Release Manager | R | P0 | Not Started | 3 | 3 | 8 | 8 | 2026-04-13 | 2026-04-15 | PRC-05 | N
SOP-12 | Procedure | DevSecOps | 2 | SOP | SOP: Emergency hotfix | Steps for urgent changes with expedited approvals and post-facto review requirements. | Hotfix SOP | Release Manager | R | P0 | Not Started | 2 | 2 | 9 | 9 | 2026-04-20 | 2026-04-21 | PLY-07 | N
SOP-13 | Procedure | Governance | 2 | SOP | SOP: Quarterly access review execution | How to export permissions, review against policy, collect signoffs, remediate and record evidence. | Access review SOP | Security/Identity Eng | R | P1 | Not Started | 2 | 2 | 11 | 11 | 2026-05-04 | 2026-05-05 | PRC-07 | N
SOP-01 | Procedure | Operations | 3 | Runbooks | Runbook template + standard structure | Create runbook template including symptoms, diagnostics, actions, rollback, escalation, and evidence capture. | Runbook template | SRE/Operations | A | P1 | Not Started | 2 | 2 | 6 | 6 | 2026-03-30 | 2026-03-31 | PRC-02 | N
SOP-02 | Procedure | Operations | 3 | Runbooks | Runbook: Authentication failures (401/403) | Step-by-step for diagnosing credential issues, secret references, token refresh, and vendor checks. | Auth failure runbook | SRE/Operations | R | P0 | Not Started | 2 | 2 | 7 | 7 | 2026-04-06 | 2026-04-07 | SOP-01,PRC-03 | N
SOP-03 | Procedure | Operations | 3 | Runbooks | Runbook: Rate limiting / 429 handling | Steps to confirm rate-limit cause, adjust throttles, reschedule, and contact vendor if needed. | 429 runbook | SRE/Operations | R | P1 | Not Started | 2 | 2 | 7 | 7 | 2026-04-06 | 2026-04-07 | SOP-01 | N
SOP-04 | Procedure | Operations | 3 | Runbooks | Runbook: Vendor outage / elevated 5xx | Steps to validate vendor outage, mitigate via retries/circuit breaker, and communicate status. | 5xx outage runbook | SRE/Operations | R | P1 | Not Started | 2 | 2 | 7 | 7 | 2026-04-06 | 2026-04-07 | SOP-01 | N
SOP-05 | Procedure | Operations | 3 | Runbooks | Runbook: Schema drift detected | Diagnose schema changes, identify breaking vs additive, quarantine rules, and escalation to owners. | Schema drift runbook | Data Engineer | R | P1 | Not Started | 2 | 2 | 8 | 8 | 2026-04-13 | 2026-04-14 | SOP-01 | N
SOP-06 | Procedure | Operations | 3 | Runbooks | Runbook: Bronze write failures (storage/permissions) | Check UC permissions, storage mount, Delta transaction errors, and recovery steps. | Bronze write failure runbook | SRE/Operations | R | P0 | Not Started | 2 | 2 | 8 | 8 | 2026-04-13 | 2026-04-14 | SOP-01 | N
SOP-19 | Procedure | Operations | 3 | Procedure | Procedure: Classify an ingestion failure (taxonomy) | Map common errors to error types, severity, and routing; ensure consistent categorization in errors table. | Error taxonomy procedure | SRE/Operations | R | P1 | Not Started | 2 | 2 | 8 | 8 | 2026-04-13 | 2026-04-14 | PLY-02 | N
SOP-07 | Procedure | Operations | 3 | Runbooks | Runbook: DLQ growth / parse failures | Identify root cause, isolate sources/endpoints, replay strategy and validation steps. | DLQ growth runbook | Data Engineer | R | P1 | Not Started | 2 | 2 | 9 | 9 | 2026-04-20 | 2026-04-21 | SOP-01 | N
SOP-21 | Procedure | Operations | 3 | Runbooks | Runbook: Config validation/publish failure | Steps to diagnose CI config validation failures and registry publish issues. | Config publish runbook | DevOps/Platform Eng | R | P1 | Not Started | 2 | 2 | 9 | 9 | 2026-04-20 | 2026-04-21 | SOP-01 | N
SOP-22 | Procedure | Operations | 3 | Runbooks | Runbook: Stuck jobs / orchestration failures | Diagnose workflow/task failures, cluster issues, concurrency limits. | Orchestration runbook | SRE/Operations | R | P1 | Not Started | 2 | 2 | 9 | 9 | 2026-04-20 | 2026-04-21 | SOP-01 | N
SOP-15 | Procedure | Operations | 3 | SOP | SOP: Alert tuning and suppression | Procedure to adjust thresholds, implement dedupe, suppression windows, and track changes. | Alert tuning SOP | SRE/Operations | R | P2 | Not Started | 2 | 2 | 10 | 10 | 2026-04-27 | 2026-04-28 | PLY-09 | N
SOP-23 | Procedure | Operations | 3 | Runbooks | Runbook: Data freshness lag breach | Diagnose lag, check schedule, rate limits, upstream delays, and mitigation. | Freshness lag runbook | SRE/Operations | R | P1 | Not Started | 2 | 2 | 10 | 10 | 2026-04-27 | 2026-04-28 | SOP-01 | N
SOP-20 | Procedure | Governance | 4 | Procedure | Procedure: Source intake form completion | Detailed instructions for requestors to complete the intake form (required fields and examples). | Intake form instructions | Product Owner | R | P2 | Not Started | 1 | 1 | 7 | 7 | 2026-04-06 | 2026-04-06 | PRC-06 | N
SOP-08 | Procedure | Operations | 4 | SOP | SOP: Source onboarding checklist (operator view) | Step-by-step to onboard a source using templates, configs, secret references and enabling schedules. | Onboarding SOP | Data Engineer | R | P1 | Not Started | 3 | 3 | 9 | 9 | 2026-04-20 | 2026-04-22 | PRC-06 | N
SOP-14 | Procedure | Operations | 4 | SOP | SOP: Backfill execution | How to run approved backfills, manage compute, validate row counts and close request with evidence. | Backfill SOP | Data Engineer | R | P2 | Not Started | 2 | 2 | 10 | 10 | 2026-04-27 | 2026-04-28 | PRC-08 | N
SOP-24 | Procedure | Operations | 5 | SOP | SOP: Retention purge job execution | How to run/verify purge jobs, validate deletions, and capture evidence. | Purge SOP | SRE/Operations | R | P2 | Not Started | 2 | 2 | 12 | 12 | 2026-05-11 | 2026-05-12 | SOP-01 | N
SOP-25 | Procedure | Operations | 5 | SOP | SOP: Compute cost anomaly investigation | Procedure to investigate cost spikes, identify offending sources, and tune schedules/throttles. | Cost anomaly SOP | SRE/Operations | R | P2 | Not Started | 2 | 2 | 13 | 13 | 2026-05-18 | 2026-05-19 | SOP-01 | N
SOP-18 | Procedure | Operations | 5 | SOP | SOP: Source decommission | How to disable pipelines, archive configs, set retention, notify stakeholders, and update registry. | Decommission SOP | Data Engineer | R | P3 | Not Started | 2 | 2 | 15 | 15 | 2026-06-01 | 2026-06-02 | PRC-12 | N
SOP-16 | Procedure | Operations | 6 | SOP | SOP: ORR execution and signoff | Step-by-step to run ORR checklist, gather evidence, and secure signoffs. | ORR SOP | SRE/Operations | R | P0 | Not Started | 2 | 2 | 12 | 12 | 2026-05-11 | 2026-05-12 | PRC-10 | N
SOP-17 | Procedure | Operations | 6 | SOP | SOP: Post-incident review (PIR) / postmortem | How to conduct PIRs, write report, track action items and update runbooks/policies. | PIR template + SOP | SRE/Operations | R | P1 | Not Started | 2 | 2 | 12 | 12 | 2026-05-11 | 2026-05-12 | PRC-02 | N
Formulas:
Start Date = Inputs!$B3+([Start Week]-1)*Inputs!$B4
End Date = [Start Date]+[Duration (days)]-1

## Design
Design – Work Breakdown Structure (WBS)
Update Status and Notes/Evidence Link during execution. Dates auto-calc from Inputs.
Task ID | Category | Workstream | Phase | Module | Task Name | Task Description | Deliverable/Artifact | Owner Role | RACI | Priority | Status | Est Effort (Person-days) | Duration (days) | Start Week | End Week | Start Date | End Date | Dependencies | Milestone (Y/N) | Notes/Evidence Link
DSN-01 | Design | Architecture | 0 | Reference Architecture | Define target reference architecture | Define control plane, compute model, bronze contract, orchestration, observability, security, lineage, and environments. | Architecture diagram + ADRs | Data Platform Architect | A | P0 | Not Started | 8 | 10 | 1 | 2 | 2026-02-23 | 2026-03-04 | PLY-01 | N
DSN-02 | Design | Control Plane | 1 | Metadata Registry | Design control plane schema (sources/endpoints/state/runs/errors) | Define Delta table schemas, keys, partitioning, indexing strategy, ownership fields, SLO fields. | Control plane data model spec | Data Platform Architect | A | P0 | Not Started | 6 | 7 | 2 | 2 | 2026-03-02 | 2026-03-08 | DSN-01 | N
DSN-03 | Design | Connector SDK | 1 | Connector Interface | Design connector SDK interface & packaging | Define connector contract methods, error handling conventions, versioning, and packaging (wheel). | Connector SDK spec | Data Engineer | R | P0 | Not Started | 5 | 6 | 2 | 2 | 2026-03-02 | 2026-03-07 | DSN-01 | N
DSN-04 | Design | Runtime | 1 | Extraction Runtime | Design extraction runtime behaviors | Retry/backoff, pagination patterns, throttling, circuit breaker, incremental strategies, idempotency/dedupe. | Runtime design spec | Data Engineer | R | P0 | Not Started | 6 | 7 | 3 | 3 | 2026-03-09 | 2026-03-15 | DSN-03 | N
DSN-05 | Design | Bronze | 1 | Bronze Contract | Design Bronze table contract | Define required metadata columns, raw payload storage type, partitioning, naming, retention hooks. | Bronze contract spec | Data Platform Architect | A | P0 | Not Started | 4 | 5 | 3 | 3 | 2026-03-09 | 2026-03-13 | DSN-02 | N
DSN-06 | Design | Orchestration | 1 | Scheduling | Design orchestration approach | Controller job vs job-per-source strategy, concurrency controls, scheduling, backfill workflow pattern. | Orchestration design spec | Data Platform Architect | A | P1 | Not Started | 4 | 5 | 3 | 3 | 2026-03-09 | 2026-03-13 | DSN-01 | N
DSN-16 | Design | Compute | 1 | Compute Policies | Design compute model & cluster policies | Define cluster/job compute, autoscaling, instance types, cost controls, cluster policies. | Compute policy design | DevOps/Platform Eng | A | P1 | Not Started | 3 | 4 | 4 | 4 | 2026-03-16 | 2026-03-19 | DSN-01 | N
DSN-18 | Design | Testing | 1 | Test Strategy | Design testing strategy (unit/integration/contract) | Define test harness, mocking patterns, golden responses, env gates, and smoke tests. | Test strategy doc | QA/Test | A | P1 | Not Started | 4 | 5 | 4 | 4 | 2026-03-16 | 2026-03-20 | DSN-03,DSN-14 | N
DSN-07 | Design | Security | 2 | Secrets & Identity | Design secrets integration & auth patterns | External secret manager integration, secret naming conventions, OAuth2 flows, token caching/refresh patterns. | Security & auth design spec | Security/Identity Eng | A | P0 | Not Started | 5 | 6 | 3 | 3 | 2026-03-09 | 2026-03-14 | PLY-03,DSN-03 | N
DSN-14 | Design | DevSecOps | 2 | CI/CD | Design CI/CD pipeline and IaC approach | Define tests, scanning, artifacts, deployment strategy, environment configs, approval gates, Terraform modules. | CI/CD & IaC design spec | DevOps/Platform Eng | A | P0 | Not Started | 6 | 7 | 4 | 4 | 2026-03-16 | 2026-03-22 | PLY-07,PLY-08 | N
DSN-15 | Design | Governance | 2 | Documentation | Design operations handbook structure | Define handbook sections: architecture, SLOs, dashboards, alerts, runbooks, on-call, escalation. | Ops handbook outline | SRE/Operations | A | P1 | Not Started | 3 | 3 | 6 | 6 | 2026-03-30 | 2026-04-01 | PRC-01,DSN-01 | N
DSN-17 | Design | Governance | 2 | Retention Implementation | Design retention purge implementation | Define purge job patterns, legal hold exceptions, and verification reporting. | Purge design spec | Data Engineer | R | P2 | Not Started | 3 | 4 | 6 | 6 | 2026-03-30 | 2026-04-02 | PLY-06 | N
DSN-08 | Design | Observability | 3 | Metrics Model | Design metrics/logging schema for observability | Define run metrics, API metrics, freshness metrics, DQ results, error taxonomy, and dimensions. | Observability data model spec | SRE/Operations | A | P0 | Not Started | 5 | 6 | 4 | 4 | 2026-03-16 | 2026-03-21 | DSN-02,PLY-09 | N
DSN-09 | Design | Alerting | 3 | Alerts | Design alert rules & routing mappings | Define alert conditions, thresholds, mapping to P0-P3, routing to platform vs domain owners, suppression logic. | Alert rules design | SRE/Operations | A | P0 | Not Started | 4 | 5 | 5 | 5 | 2026-03-23 | 2026-03-27 | DSN-08,PLY-02 | N
DSN-10 | Design | Data Quality | 3 | DQ Framework | Design DQ framework at ingest boundary | Define rule types, severity levels (warn/quarantine/fail), configuration storage, and reporting. | DQ design spec | Data Engineer | R | P1 | Not Started | 4 | 5 | 5 | 5 | 2026-03-23 | 2026-03-27 | DSN-02 | N
DSN-11 | Design | DLQ/Replay | 3 | Error Handling | Design DLQ and replay mechanisms | Define DLQ table schema, replay job patterns, replay by run_id/window, and audit logging. | DLQ/Replay design spec | Data Engineer | R | P1 | Not Started | 4 | 5 | 5 | 5 | 2026-03-23 | 2026-03-27 | DSN-10 | N
DSN-12 | Design | Schema Evolution | 3 | Schema Drift | Design schema drift detection and evolution policy | Define detection approach, versioning, breaking change handling, quarantine workflows and alerts. | Schema drift design spec | Data Platform Architect | A | P1 | Not Started | 4 | 5 | 6 | 6 | 2026-03-30 | 2026-04-03 | DSN-05,PLY-14 | N
DSN-13 | Design | Lineage | 3 | Audit & Lineage | Design auditing and lineage approach | Define audit events, evidence tables, UC lineage usage, optional OpenLineage emission pattern. | Audit & lineage design spec | Data Platform Architect | A | P1 | Not Started | 4 | 5 | 6 | 6 | 2026-03-30 | 2026-04-03 | PLY-16 | N
DSN-19 | Design | Onboarding Factory | 4 | Templates | Design onboarding templates and automation | Define config templates, vendor profiles, bulk onboarding approach and validation rules. | Onboarding templates design | Data Engineer | R | P1 | Not Started | 4 | 5 | 7 | 7 | 2026-04-06 | 2026-04-10 | PRC-06,PRC-13 | N
DSN-20 | Design | Cost/FinOps | 5 | Cost Attribution | Design cost attribution per source | Define how to attribute compute/storage to sources (tags, job run metadata) and dashboard. | Cost attribution design | DevOps/Platform Eng | A | P2 | Not Started | 3 | 4 | 10 | 10 | 2026-04-27 | 2026-04-30 | DSN-08 | N
Formulas:
Start Date = Inputs!$B3+([Start Week]-1)*Inputs!$B4
End Date = [Start Date]+[Duration (days)]-1

## Implementation
Implementation – Work Breakdown Structure (WBS)
Update Status and Notes/Evidence Link during execution. Dates auto-calc from Inputs.
Task ID | Category | Workstream | Phase | Module | Task Name | Task Description | Deliverable/Artifact | Owner Role | RACI | Priority | Status | Est Effort (Person-days) | Duration (days) | Start Week | End Week | Start Date | End Date | Dependencies | Milestone (Y/N) | Notes/Evidence Link
IMP-01 | Implementation | Planning | 0 | Discovery | Inventory current API ingestions & patterns | Catalogue existing sources/endpoints/auth/pagination; group into patterns; identify pilot candidates. | API inventory + pattern matrix | Data Engineer | R | P1 | Not Started | 6 | 8 | 1 | 2 | 2026-02-23 | 2026-03-02 | PLY-01 | N | Include rate limits, volumes, SLAs where known.
IMP-02 | Implementation | Planning | 0 | Discovery | Define Tier-0/1/2 source list | Create initial tiering with business owners and SLO expectations. | Tiered source list | Product Owner | A | P1 | Not Started | 3 | 4 | 2 | 2 | 2026-03-02 | 2026-03-05 | PRC-15 | N
IMP-03 | Implementation | Control Plane | 1 | Metadata Registry | Implement registry Delta tables (sources/endpoints/state/runs/errors) | Create schemas in UC, apply permissions, implement migrations/versioning approach. | Control plane tables in UC | Data Engineer | R | P0 | Not Started | 8 | 10 | 3 | 4 | 2026-03-09 | 2026-03-18 | DSN-02,PLY-11 | N
IMP-05 | Implementation | Connector SDK | 1 | Connector Interface | Build connector SDK base package | Implement interfaces, standard exceptions, logging hooks, metrics hooks and packaging. | Connector SDK v1 | Data Engineer | R | P0 | Not Started | 10 | 12 | 3 | 4 | 2026-03-09 | 2026-03-20 | DSN-03,DSN-18 | N
IMP-55 | Implementation | Architecture | 1 | Reviews | Architecture review & signoff | Review architecture and ADRs with stakeholders; capture decisions and action items. | Architecture signoff | Data Platform Architect | A | P1 | Not Started | 2 | 2 | 3 | 3 | 2026-03-09 | 2026-03-10 | DSN-01 | Y
IMP-04 | Implementation | Control Plane | 1 | Metadata Registry | Implement config validation and publish pipeline | Build CI job to validate configs and publish to registry tables in each environment. | Config publish pipeline | DevOps/Platform Eng | R | P1 | Not Started | 6 | 8 | 4 | 5 | 2026-03-16 | 2026-03-23 | DSN-14,PRC-13 | N
IMP-06 | Implementation | Connector SDK | 1 | Connector Templates | Implement connector template: REST API key | Provide reusable template supporting headers, params, pagination and incremental watermark. | REST API key connector template | Data Engineer | R | P1 | Not Started | 5 | 6 | 4 | 4 | 2026-03-16 | 2026-03-21 | IMP-05 | N
IMP-07 | Implementation | Connector SDK | 1 | Connector Templates | Implement connector template: OAuth2 client credentials | Template for OAuth2 flows with token caching/refresh; supports vendor profiles. | OAuth2 connector template | Data Engineer | R | P0 | Not Started | 6 | 7 | 4 | 4 | 2026-03-16 | 2026-03-22 | IMP-05,IMP-16 | N
IMP-08 | Implementation | Runtime | 1 | Extraction Runtime | Implement HTTP client with retries/backoff/jitter | Standard HTTP layer handling 429/5xx/4xx policies and telemetry. | Resilient HTTP client | Data Engineer | R | P0 | Not Started | 6 | 7 | 4 | 4 | 2026-03-16 | 2026-03-22 | DSN-04 | N
IMP-13 | Implementation | Bronze | 1 | Bronze Contract | Create Bronze databases/schemas and naming conventions | Set up UC catalogs/schemas for bronze and ingestion control tables; permission templates. | UC schemas + conventions applied | Data Platform Architect | A | P0 | Not Started | 4 | 5 | 4 | 4 | 2026-03-16 | 2026-03-20 | DSN-05,PLY-11 | N
IMP-09 | Implementation | Runtime | 1 | Extraction Runtime | Implement pagination strategies | Support page number, next-token, cursor-based pagination as configurable strategies. | Pagination module | Data Engineer | R | P0 | Not Started | 6 | 7 | 5 | 5 | 2026-03-23 | 2026-03-29 | IMP-08 | N
IMP-10 | Implementation | Runtime | 1 | Extraction Runtime | Implement incremental load strategies + checkpointing | Support watermark timestamp, since_id, delta token; persist checkpoints in ingestion.state. | Incremental + checkpoint module | Data Engineer | R | P0 | Not Started | 7 | 9 | 5 | 6 | 2026-03-23 | 2026-03-31 | IMP-03,IMP-08 | N
IMP-14 | Implementation | Bronze | 1 | Bronze Contract | Implement Bronze writer (Delta) with metadata columns | Write raw_payload + ingest metadata; idempotency with payload_hash/record_id; batch write patterns. | Bronze writer module | Data Engineer | R | P0 | Not Started | 6 | 8 | 5 | 6 | 2026-03-23 | 2026-03-30 | IMP-13,DSN-05 | N
IMP-11 | Implementation | Runtime | 1 | Extraction Runtime | Implement rate limiting / throttling controls | Global concurrency limits + per-vendor QPS caps; config-driven. | Throttling module | Data Engineer | R | P1 | Not Started | 5 | 6 | 6 | 6 | 2026-03-30 | 2026-04-04 | IMP-08,DSN-20 | N
IMP-12 | Implementation | Runtime | 1 | Extraction Runtime | Implement circuit breaker & vendor outage handling | Stop hammering failing vendors; mark degraded; auto-recover; emit alerts. | Circuit breaker module | Data Engineer | R | P1 | Not Started | 4 | 5 | 6 | 6 | 2026-03-30 | 2026-04-03 | IMP-08 | N
IMP-20 | Implementation | Orchestration | 1 | Workflows | Implement controller workflow (fan-out per source/endpoint) | Read registry and create tasks with concurrency limits; support retries and backfill runs. | Controller workflow | Data Engineer | R | P0 | Not Started | 8 | 10 | 6 | 7 | 2026-03-30 | 2026-04-08 | IMP-03,DSN-06,IMP-11 | N
IMP-21 | Implementation | Testing | 1 | Test Harness | Build connector test harness with mock server | Provide mock API server + golden responses; integration tests for templates. | Connector test harness | QA/Test | A | P1 | Not Started | 6 | 8 | 6 | 7 | 2026-03-30 | 2026-04-06 | DSN-18,IMP-05 | N
IMP-37 | Implementation | Compute | 1 | Compute Policies | Implement cluster/job compute policies | Configure cluster policies, autoscaling constraints, tagging for cost attribution. | Compute policies enforced | DevOps/Platform Eng | R | P1 | Not Started | 4 | 5 | 7 | 7 | 2026-04-06 | 2026-04-10 | DSN-16 | N
IMP-57 | Implementation | MVP | 1 | Engine MVP | MVP engine end-to-end demo (2 sources) | Demonstrate config-driven ingestion for 2 sources with checkpoints, Bronze writes, metrics, and reruns. | MVP demo evidence | Data Engineer | R | P0 | Not Started | 2 | 2 | 8 | 8 | 2026-04-13 | 2026-04-14 | IMP-05,IMP-10,IMP-14,IMP-23 | Y
IMP-15 | Implementation | Security | 2 | Secrets & Identity | Integrate external secret manager with Databricks secret scopes | Configure secret scopes, references, naming conventions across dev/stage/prod. | Secret manager integration | Security/Identity Eng | A | P0 | Not Started | 6 | 7 | 4 | 4 | 2026-03-16 | 2026-03-22 | DSN-07 | N
IMP-18 | Implementation | DevSecOps | 2 | CI/CD | Implement CI pipeline (tests, lint, packaging) | Build pipeline running unit tests, static checks, dependency scanning, package artifacts. | CI pipeline live | DevOps/Platform Eng | R | P0 | Not Started | 7 | 9 | 4 | 5 | 2026-03-16 | 2026-03-24 | DSN-14,DSN-18 | N
IMP-16 | Implementation | Security | 2 | Secrets & Identity | Implement auth handlers (OAuth2/API key) in runtime | Add auth middleware, token caching, refresh scheduling and safe logging (no secrets). | Auth modules implemented | Data Engineer | R | P0 | Not Started | 6 | 7 | 5 | 5 | 2026-03-23 | 2026-03-29 | IMP-16,IMP-07 | N
IMP-17 | Implementation | Security | 2 | Secrets & Identity | Implement service principals for jobs + UC permissions | Create SPNs, assign policies, grant UC permissions, attach to workflows. | Service principals in place | Security/Identity Eng | A | P0 | Not Started | 5 | 6 | 5 | 5 | 2026-03-23 | 2026-03-28 | SOP-09,PLY-11 | N
IMP-19 | Implementation | DevSecOps | 2 | CD/IaC | Implement IaC for Jobs/Workflows/Permissions | Terraform modules for jobs, clusters, permissions, secret scope references, env configs. | IaC baseline | DevOps/Platform Eng | R | P1 | Not Started | 8 | 10 | 6 | 7 | 2026-03-30 | 2026-04-08 | IMP-19,DSN-14 | N
IMP-34 | Implementation | Governance | 2 | Permissions | Implement UC permission templates (by classification/tier) | Create groups and grants for Bronze/metrics/audit; map to data classification. | UC permissions applied | Security/Identity Eng | A | P0 | Not Started | 5 | 6 | 7 | 7 | 2026-04-06 | 2026-04-11 | PLY-05,PLY-11,IMP-17 | N
IMP-56 | Implementation | Security | 2 | Reviews | Security design review & signoff | Review secrets, identities, access control, logging and rotation; address findings. | Security review signoff | Security/Identity Eng | A | P0 | Not Started | 3 | 3 | 7 | 7 | 2026-04-06 | 2026-04-08 | IMP-16,IMP-17,PLY-16 | Y
IMP-33 | Implementation | Governance | 2 | Documentation | Publish Policies & Processes set (approved) | Create documents, run approvals, publish in central repository with versioning. | Approved governance docs | Product Owner | A | P0 | Not Started | 6 | 8 | 8 | 9 | 2026-04-13 | 2026-04-20 | PLY-01,PLY-02,PLY-03,PLY-07,PRC-01 | N
IMP-36 | Implementation | DevSecOps | 2 | CD | Implement CD pipeline (deploy dev/stage/prod with gates) | Automate deployments of jobs, libraries and configs with approvals and smoke tests. | CD pipeline live | DevOps/Platform Eng | R | P0 | Not Started | 8 | 10 | 8 | 9 | 2026-04-13 | 2026-04-22 | IMP-20,IMP-19 | N
IMP-32 | Implementation | Governance | 2 | Documentation | Draft Operations Handbook v1 | Create handbook: architecture, SLOs, dashboards, alerts, runbooks, escalation, release process. | Ops handbook v1 | SRE/Operations | A | P1 | Not Started | 5 | 6 | 9 | 9 | 2026-04-20 | 2026-04-25 | DSN-15,IMP-24 | N
IMP-38 | Implementation | Security | 2 | Monitoring | Implement security audit logs and monitoring | Capture permission changes, secret scope changes, deploy events; integrate with SIEM if applicable. | Security monitoring live | Security/Identity Eng | A | P1 | Not Started | 5 | 6 | 9 | 9 | 2026-04-20 | 2026-04-25 | PLY-16,IMP-32 | N
IMP-35 | Implementation | Governance | 2 | Retention | Implement retention purge jobs | Scheduled jobs to enforce Bronze/log/DLQ retention with audit evidence. | Retention jobs live | Data Engineer | R | P1 | Not Started | 4 | 5 | 11 | 11 | 2026-05-04 | 2026-05-08 | DSN-17,PLY-06 | N
IMP-22 | Implementation | Observability | 3 | Metrics | Implement metrics tables and logging | Create ingestion.runs, ingestion.metrics, ingestion.errors population and standardized logging. | Metrics+logs implemented | Data Engineer | R | P0 | Not Started | 6 | 8 | 6 | 7 | 2026-03-30 | 2026-04-06 | DSN-08,IMP-03 | N
IMP-61 | Implementation | Reliability | 3 | Idempotency | Implement deduplication/idempotency strategy | Implement payload hashing/record keys and merge strategy where needed; document per-source approach. | Idempotency implemented | Data Engineer | R | P0 | Not Started | 4 | 6 | 6 | 6 | 2026-03-30 | 2026-04-04 | IMP-14,IMP-10 | N
IMP-23 | Implementation | Observability | 3 | Dashboards | Build Ops dashboard (runs, failures, lag, DLQ) | Create dashboards in chosen tooling (DBSQL/Lakeview/etc.) for ops use. | Ops dashboard v1 | SRE/Operations | A | P0 | Not Started | 5 | 6 | 8 | 8 | 2026-04-13 | 2026-04-18 | IMP-23 | N
IMP-26 | Implementation | Data Quality | 3 | DQ Framework | Implement DQ rule engine (config-driven) | Implement rules evaluation and results table, enforcement modes (warn/quarantine/fail). | DQ engine v1 | Data Engineer | R | P1 | Not Started | 7 | 9 | 8 | 9 | 2026-04-13 | 2026-04-21 | DSN-10,IMP-03 | N
IMP-62 | Implementation | Operations | 3 | Tickets | Set up ticket queues and templates (Incidents/Requests) | Create Jira/ADO templates for incidents, backfill requests, onboarding requests and access reviews. | Ticket templates live | Product Owner | A | P2 | Not Started | 2 | 2 | 8 | 8 | 2026-04-13 | 2026-04-14 | PLY-02,PRC-02,PRC-06 | N
IMP-24 | Implementation | Observability | 3 | Dashboards | Build Exec dashboard (SLO compliance, top offenders) | High level view; includes tiering filters and trends. | Exec dashboard v1 | Product Owner | A | P1 | Not Started | 4 | 5 | 9 | 9 | 2026-04-20 | 2026-04-24 | IMP-24,PLY-10 | N
IMP-25 | Implementation | Alerting | 3 | Alerts | Implement alert rules + routing | Create alert rules mapped to P0-P3; configure routing to on-call and owners. | Alerts live | SRE/Operations | A | P0 | Not Started | 6 | 7 | 9 | 9 | 2026-04-20 | 2026-04-26 | DSN-09,IMP-23 | N
IMP-27 | Implementation | DLQ/Replay | 3 | DLQ | Implement DLQ tables + writer | Write failing records and context to DLQ; link to runs/errors; retention. | DLQ implemented | Data Engineer | R | P1 | Not Started | 5 | 6 | 9 | 9 | 2026-04-20 | 2026-04-25 | DSN-11,IMP-27 | N
IMP-29 | Implementation | Schema Evolution | 3 | Schema Drift | Implement schema drift detection | Detect schema changes (add/remove/type), record versions, quarantine breaking changes. | Schema drift detector v1 | Data Engineer | R | P1 | Not Started | 6 | 8 | 9 | 10 | 2026-04-20 | 2026-04-27 | DSN-12,IMP-14 | N
IMP-30 | Implementation | Lineage | 3 | Audit & Lineage | Implement audit logging tables and events | Populate audit events: deploy versions, config versions, secret references, table writes. | Audit logging v1 | Data Engineer | R | P1 | Not Started | 5 | 6 | 10 | 10 | 2026-04-27 | 2026-05-02 | DSN-13,IMP-23 | N
IMP-58 | Implementation | Observability | 3 | Go-live | Observability framework go-live (dashboards + alerts) | Go-live with dashboards, alerts, routing and runbooks; validate alert storms suppressed. | Observability live | SRE/Operations | A | P0 | Not Started | 2 | 2 | 10 | 10 | 2026-04-27 | 2026-04-28 | IMP-24,IMP-26,SOP-16 | Y
IMP-31 | Implementation | Lineage | 3 | Audit & Lineage | Enable UC lineage + validate critical flows | Ensure pipelines register lineage; validate on key bronze tables; document limitations. | Lineage enabled + validated | Data Platform Architect | A | P2 | Not Started | 3 | 4 | 11 | 11 | 2026-05-04 | 2026-05-07 | IMP-32 | N
IMP-60 | Implementation | Schema Evolution | 3 | Policy Enforcement | Implement schema quarantine pipeline | When breaking changes detected, quarantine affected sources/endpoints and notify owners; allow override approvals. | Schema quarantine workflow | Data Engineer | R | P1 | Not Started | 4 | 5 | 11 | 11 | 2026-05-04 | 2026-05-08 | IMP-31,IMP-26 | N
IMP-59 | Implementation | Governance | 4 | Onboarding | Implement source intake form (template + storage) | Create standardized intake form (Confluence/Sharepoint) and storage; link into onboarding process. | Intake form published | Product Owner | A | P1 | Not Started | 2 | 2 | 7 | 7 | 2026-04-06 | 2026-04-07 | PRC-06,SOP-21 | N
IMP-39 | Implementation | Pilot | 4 | Pilot Onboarding | Pilot onboarding - Source 1–3 (mixed auth) | Onboard first set of sources covering API key and OAuth2 patterns; verify SLOs and runbooks. | 3 pilot sources in prod | Data Engineer | R | P0 | Not Started | 10 | 10 | 9 | 10 | 2026-04-20 | 2026-04-29 | IMP-21,IMP-07,IMP-23,IMP-24 | Y
IMP-28 | Implementation | DLQ/Replay | 4 | Replay | Implement replay tooling (by run_id/window/DLQ) | Jobs/notebooks for safe replay; ensure idempotency; capture evidence. | Replay tooling | Data Engineer | R | P1 | Not Started | 5 | 6 | 10 | 10 | 2026-04-27 | 2026-05-02 | IMP-28,IMP-10 | N
IMP-40 | Implementation | Pilot | 4 | Pilot Onboarding | Pilot onboarding - Source 4–8 (pagination + rate limits) | Onboard sources with complex pagination and strict rate limits; tune throttling; validate alerts. | 8 pilot sources total | Data Engineer | R | P0 | Not Started | 12 | 12 | 10 |  |  |  | IMP-42,IMP-26 | N
IMP-42 | Implementation | Testing | 4 | Contract Tests | Implement contract tests for pilot APIs | Create schema/response contract tests for pilot sources; schedule daily checks in non-prod. | Pilot contract tests | QA/Test | A | P1 | Not Started | 6 | 8 | 10 |  |  |  | IMP-22,IMP-43 | N
IMP-41 | Implementation | Pilot | 4 | Pilot Validation | Pilot stabilization period (2 weeks) | Operate pilot with on-call processes; fix defects; finalize templates and thresholds. | Pilot stability report | SRE/Operations | A | P0 | Not Started | 8 | 10 | 11 |  |  |  | IMP-43 | Y
IMP-45 | Implementation | Scale-out | 5 | Wave 1 | Wave 1 onboarding (20 APIs) | Onboard next 20 standard-pattern APIs using templates; measure throughput and incident rate. | 20 new APIs live | Data Engineer | R | P1 | Not Started | 20 | 10 | 14 |  |  |  | IMP-44,DSN-19 | N
IMP-46 | Implementation | Scale-out | 5 | Wave 1 | Wave 1 retrospectives + template improvements | Review onboarding pain points; improve templates, docs, dashboards; tune defaults. | Improvement backlog + releases | Data Platform Architect | A | P2 | Not Started | 5 | 5 | 16 |  |  |  | IMP-49 | N
IMP-50 | Implementation | Scale-out | 5 | Automation | Build bulk onboarding helper (config generator) | Tooling (notebook/UI) to generate validated configs and vendor profiles from intake forms. | Bulk onboarding tool | Data Engineer | R | P2 | Not Started | 8 | 10 | 16 |  |  |  | DSN-19,IMP-35 | N
IMP-47 | Implementation | Scale-out | 5 | Wave 2 | Wave 2 onboarding (30 APIs) | Onboard 30 APIs (mixed complexity). Ensure owners assigned and SLOs configured. | 30 more APIs live | Data Engineer | R | P1 | Not Started | 30 | 15 | 17 |  |  |  | IMP-50 | N
IMP-49 | Implementation | Scale-out | 5 | Operations | Implement cost attribution dashboard (showback) | Dashboard compute/storage per source/vendor; identify top spenders; feed to tuning. | Cost dashboard | DevOps/Platform Eng | A | P2 | Not Started | 6 | 7 | 18 |  |  |  | DSN-20,IMP-23 | N
IMP-51 | Implementation | Scale-out | 5 | Quality | Enhance anomaly detection on volume/freshness | Add baseline anomaly detection (counts/lag) and alert on deviations; tune thresholds. | Anomaly detection v1 | SRE/Operations | A | P2 | Not Started | 6 | 8 | 19 |  |  |  | IMP-26 | N
IMP-48 | Implementation | Scale-out | 5 | Wave 3 | Wave 3 onboarding (40 APIs) | Onboard 40 APIs; include higher complexity; expand vendor profiles; enforce gates. | 40 more APIs live | Data Engineer | R | P2 | Not Started | 40 | 20 | 20 |  |  |  | IMP-51 | N
IMP-63 | Implementation | Governance | 5 | Decommission | Tag and track deprecated/unused sources | Add registry fields and reports for unused sources; prepare for decommission wave. | Deprecated sources report | Data Engineer | R | P3 | Not Started | 2 | 3 | 21 |  |  |  | IMP-03 | N
IMP-52 | Implementation | Scale-out | 5 | Governance | Implement decommission workflow automation | Automate disabling schedules, archiving configs, and updating registry status. | Decommission automation | DevOps/Platform Eng | R | P3 | Not Started | 4 | 5 | 22 |  |  |  | PRC-12 | N
IMP-43 | Implementation | Operations | 6 | ORR | Execute Operational Readiness Review (ORR) | Run ORR checklist, ensure runbooks, SLOs, alerts, permissions, DR tested; obtain signoff. | ORR signoff | SRE/Operations | A | P0 | Not Started | 5 | 5 | 13 |  |  |  | PRC-10,IMP-44,IMP-34 | Y
IMP-44 | Implementation | Operations | 6 | Game Days | Conduct game days (token expiry, vendor outage, schema break) | Simulate failures, validate alert routing, runbooks, and recovery procedures; capture actions. | Game day evidence pack | SRE/Operations | A | P1 | Not Started | 5 | 6 | 13 |  |  |  | PRC-11,IMP-46 | N
IMP-53 | Implementation | Operations | 6 | Handover | Ops training + handover to run team | Training sessions for on-call, walk through dashboards/runbooks, define steady-state rituals. | Handover complete | SRE/Operations | A | P1 | Not Started | 4 | 4 | 14 |  |  |  | IMP-46 | N
IMP-54 | Implementation | Operations | 6 | Documentation | Finalize operations handbook and runbook set | Incorporate lessons from pilot and game days; publish final versions; set review cadence. | Ops docs v1.0 | SRE/Operations | A | P1 | Not Started | 4 | 5 | 14 |  |  |  | IMP-34,IMP-47 | N
Formulas:
Start Date = Inputs!$B3+([Start Week]-1)*Inputs!$B4
End Date = [Start Date]+[Duration (days)]-1

## Summary
Summary – counts, effort, milestones
Effort by Category |  |  |  | Key KPIs
Category | Tasks (#) | Effort (PD) | % of Effort | Total tasks | 47
Policy | 0 | 0 | 0% | Total effort (PD) | 8
Process | 0 | 0 | 0% | Milestones (#) | 3
Procedure | 0 | 0 | 0%
Design | 20 | 8 | 100%
Implementation | 27 | 0 | 0%
TOTAL | 47 | 8 | 100%
Effort by Phase
Phase | Tasks (#) | Effort (PD)
0 | 3 | 0
1 | 24 | 0
2 | 12 | 0
3 | 6 | 0
4 | 1 | 0
5 | 1 | 0
6 | 0 | 0
TOTAL | 47 | 0
Milestones
Task ID | Milestone | Planned End Date | Owner
IMP-55 | Architecture review & signoff | 46091 | Data Platform Architect
IMP-57 | MVP engine end-to-end demo (2 sources) | 46126 | Data Engineer
IMP-56 | Security design review & signoff | 46120 | Security/Identity Eng
IMP-58 | 42 | 1900-02-10 | 42
IMP-39 | 42 | 1900-02-10 | 42
IMP-41 | 42 | 1900-02-10 | 42
IMP-43 | 42 | 1900-02-10 | 42
Formulas:
Effort (PD) = INDEX(Master!$R4:R141,MATCH([Phase],Master!$A4:A141,0))

## Governance_Register
Governance Artifact Register (audit-ready)
Track policies, processes, procedures/runbooks, design specs and handbook. Fill Doc Link & Evidence Link.
Artifact ID | Type | Name | Description | Owner | Approver | Status | Version | Review Cadence (months) | Next Review Date | Doc Link | Evidence Link | Related Task IDs
POL-001 | Policy | Incident severity & defect prioritization (P0–P3) | Defines P0–P3, response SLAs, escalation and routing rules. | SRE/Operations | Product Owner | Draft | 0.1 | 6 |  |  |  | PLY-02
POL-002 | Policy | Service account & credential policy | No personal tokens; service principals; least privilege; audit requirements. | Security/Identity Eng | Security/Identity Eng | Draft | 0.1 | 6 |  |  |  | PLY-03
POL-003 | Policy | Credential rotation policy | Rotation frequency, emergency rotation, break-glass, audit evidence. | Security/Identity Eng | Security/Identity Eng | Draft | 0.1 | 6 |  |  |  | PLY-04
POL-004 | Policy | Alerting & routing policy | Paging vs ticketing, quiet hours, dedupe/suppression, escalation paths. | SRE/Operations | Product Owner | Draft | 0.1 | 6 |  |  |  | PLY-09
POL-005 | Policy | Data classification policy | Classification levels, PII handling, encryption/masking and access rules. | Security/Identity Eng | Security/Identity Eng | Draft | 0.1 | 6 |  |  |  | PLY-05
POL-006 | Policy | Retention policy (Bronze/logs/audit) | Retention periods and purge requirements; legal hold exceptions. | Data Platform Architect | Security/Identity Eng | Draft | 0.1 | 6 |  |  |  | PLY-06
POL-007 | Policy | Change & release management policy | Promotion gates, approvals, freeze windows, hotfix rules and rollback expectations. | Release Manager | Product Owner | Draft | 0.1 | 6 |  |  |  | PLY-07
POL-008 | Policy | Access control policy (Unity Catalog) | Who can read/write Bronze/metrics; access review cadence. | Security/Identity Eng | Security/Identity Eng | Draft | 0.1 | 6 |  |  |  | PLY-11
POL-009 | Policy | SLO policy (availability/freshness/latency) | SLO targets by tier and measurement approach. | Product Owner | Product Owner | Draft | 0.1 | 6 |  |  |  | PLY-10
POL-010 | Policy | Onboarding acceptance criteria policy | Mandatory metadata and tests required before production enablement. | Data Platform Architect | Product Owner | Draft | 0.1 | 6 |  |  |  | PLY-14
PRC-001 | Process | Incident triage workflow | Triage, severity assignment, communications, escalation and closure. | SRE/Operations | Product Owner | Draft | 0.1 | 6 |  |  |  | PRC-02
PRC-002 | Process | Alert response workflow | Acknowledge, investigate, mitigate, handoff to owners, close. | SRE/Operations | Product Owner | Draft | 0.1 | 6 |  |  |  | PRC-03
PRC-003 | Process | Credential rotation workflow | Rotation run, smoke tests, rollback and evidence capture. | Security/Identity Eng | Security/Identity Eng | Draft | 0.1 | 6 |  |  |  | PRC-04
PRC-004 | Process | Release promotion workflow (Dev→Stage→Prod) | CI/CD stages, approvals, automated checks, verification and rollback. | Release Manager | Product Owner | Draft | 0.1 | 6 |  |  |  | PRC-05
PRC-005 | Process | Source onboarding workflow | Intake → validation → secrets → config publish → test → prod → handover. | Data Platform Architect | Product Owner | Draft | 0.1 | 6 |  |  |  | PRC-06
PRC-006 | Process | Access review workflow | Quarterly review, signoff, remediation and evidence. | Security/Identity Eng | Security/Identity Eng | Draft | 0.1 | 6 |  |  |  | PRC-07
PRC-007 | Process | Backfill request workflow | Intake, approvals, execution, validation and cost tracking. | Data Engineer | Product Owner | Draft | 0.1 | 6 |  |  |  | PRC-08
PRC-008 | Process | DLQ reprocessing workflow | Criteria, approvals, replay steps and verification. | SRE/Operations | Product Owner | Draft | 0.1 | 6 |  |  |  | PRC-09
PRC-009 | Process | Operational Readiness Review (ORR) workflow | Checklist, gates, evidence and signoff. | SRE/Operations | Product Owner | Draft | 0.1 | 6 |  |  |  | PRC-10
SOP-001 | Procedure | Runbook template | Standard template for all runbooks with evidence capture. | SRE/Operations | SRE/Operations | Draft | 0.1 | 6 |  |  |  | SOP-01
RB-001 | Runbook | Auth failures (401/403) | Diagnose token/secret issues; rotation steps and escalation. | SRE/Operations | SRE/Operations | Draft | 0.1 | 6 |  |  |  | SOP-02
RB-002 | Runbook | Rate limiting / 429 | Identify limit causes; tune throttling/schedule; vendor escalation. | SRE/Operations | SRE/Operations | Draft | 0.1 | 6 |  |  |  | SOP-03
RB-003 | Runbook | Vendor outage / 5xx | Circuit breaker behavior, comms, and recovery actions. | SRE/Operations | SRE/Operations | Draft | 0.1 | 6 |  |  |  | SOP-04
RB-004 | Runbook | Schema drift detected | Detect, quarantine, approve override; notify owners. | Data Engineer | Data Platform Architect | Draft | 0.1 | 6 |  |  |  | SOP-05
RB-005 | Runbook | DLQ growth / parse failures | Root cause analysis, replay strategy and verification. | Data Engineer | SRE/Operations | Draft | 0.1 | 6 |  |  |  | SOP-07
SOP-010 | Procedure | Credential rotation SOP | Step-by-step rotation execution with smoke tests and evidence. | Security/Identity Eng | Security/Identity Eng | Draft | 0.1 | 6 |  |  |  | SOP-10
SOP-011 | Procedure | Production deployment SOP | Standard release promotion and verification. | Release Manager | Release Manager | Draft | 0.1 | 6 |  |  |  | SOP-11
SOP-014 | Procedure | Backfill SOP | Backfill execution procedure. | Data Engineer | Product Owner | Draft | 0.1 | 6 |  |  |  | SOP-14
DSN-001 | Design | Reference architecture | Control plane, runtime, orchestration, governance, observability, lineage. | Data Platform Architect | Product Owner | Draft | 0.1 | 6 |  |  |  | DSN-01
DSN-002 | Design | Control plane data model | Registry tables: sources/endpoints/state/runs/errors/dq/audit. | Data Platform Architect | Data Platform Architect | Draft | 0.1 | 6 |  |  |  | DSN-02
DSN-003 | Design | Connector SDK spec | Connector interface, packaging, error conventions. | Data Engineer | Data Platform Architect | Draft | 0.1 | 6 |  |  |  | DSN-03
DSN-004 | Design | Runtime spec | Retries, pagination, throttling, incremental, idempotency. | Data Engineer | Data Platform Architect | Draft | 0.1 | 6 |  |  |  | DSN-04
DSN-005 | Design | Observability metrics model | Metrics schema and dimensions supporting dashboards/alerts. | SRE/Operations | Data Platform Architect | Draft | 0.1 | 6 |  |  |  | DSN-08
DSN-006 | Design | DQ framework spec | Rule types, enforcement, reporting. | Data Engineer | Data Platform Architect | Draft | 0.1 | 6 |  |  |  | DSN-10
DSN-007 | Design | Audit & lineage spec | Audit events, evidence tables, UC lineage coverage. | Data Platform Architect | Security/Identity Eng | Draft | 0.1 | 6 |  |  |  | DSN-13
DSN-008 | Design | CI/CD & IaC spec | Pipelines, scanning, approval gates, Terraform modules. | DevOps/Platform Eng | Release Manager | Draft | 0.1 | 6 |  |  |  | DSN-14
OPS-001 | Handbook | Operations Handbook | How to operate the ingestion platform: SLOs, dashboards, alerts, runbooks, escalation. | SRE/Operations | Product Owner | Draft | 0.1 | 6 |  |  |  | IMP-34
Formulas:
Next Review Date = IF([Status]<>"Approved","",EDATE(TODAY(),[Review Cadence (months)]))

## RACI
RACI Matrix (starter)
Customize roles and responsibilities to match your org.
Activity | Product Owner | Data Platform Architect | Data Engineer | DevOps/Platform Eng | Security/Identity Eng | SRE/Operations | Domain Data Owner | QA/Test | Release Manager
Source onboarding | A | C | R | C | C | C | A/R | C | C
Credential rotation | C | C | C | C | A/R | C | I | I | I
Incident response P0/P1 | C | C | R | C | C | A/R | C | I | C
Alert tuning | I | C | C | C | C | A/R | C | I | I
Release promotion to Prod | C | C | C | R | C | C | I | C | A/R
Access review | I | C | I | I | A/R | C | C | I | I
Backfill execution | C | C | R | C | I | C | C | I | I
Decommission source | A | C | R | C | C | C | C | I | I
Runbook maintenance | C | C | R | C | C | A/R | C | I | C

## RAID
RAID Log (Risks, Assumptions, Issues, Dependencies)
Use this to track program risks and blockers during delivery.
ID | Type | Description | Impact | Likelihood | Severity | Owner | Mitigation/Plan | Status | Target Date
R-01 | Risk | API vendor rate limits constrain schedules and cause freshness lag. | High | Medium | High | Data Engineer | Implement throttling/vendor profiles; negotiate higher limits; stagger schedules. | Open
R-02 | Risk | Unclear source ownership leads to stalled onboarding and unresolved defects. | High | High | High | Product Owner | Enforce onboarding gate: owner + SLA required; assign domain owners early. | Open
R-03 | Risk | Credential rotation not automated leading to outages. | High | Medium | High | Security/Identity Eng | Implement rotation SOP + calendar reminders; automate where possible. | Open
R-04 | Risk | Schema drift causes frequent pipeline breaks and DLQ growth. | Medium | High | High | Data Platform Architect | Schema drift detection + quarantine + alerts; contract tests for critical sources. | Open
R-05 | Risk | Observability gaps cause delayed detection of failures. | High | Medium | High | SRE/Operations | Implement metrics + dashboards + alerts before scaling onboarding. | Open
A-01 | Assumption | Unity Catalog is enabled and will be the governance control plane. |  |  |  | Data Platform Architect | If not, define alternative ACL/governance approach. | Open
D-01 | Dependency | External secret manager access and enterprise onboarding approvals. |  |  |  | Security/Identity Eng | Start approvals in Phase 0; track lead times. | Open
I-01 | Issue | (placeholder) |  |  |  | SRE/Operations |  | Open

## Onboarding_Waves
Onboarding Waves (scale-out plan)
Adjust API counts and staffing assumptions; link to Master tasks IMP-49..IMP-52.
Wave | Start Week | End Week | Planned APIs | Mix (Std/Complex) | Assumed Eng FTE | Est PD per API | Total Effort (PD) | Notes
Pilot | 9 | 12 | 8 | 5/3 | 3 | 2.5 | 20
Wave 1 | 14 | 16 | 20 | 16/4 | 4 | 2 | 40
Wave 2 | 17 | 19 | 30 | 22/8 | 5 | 2.2 | 66
Wave 3 | 20 | 24 | 40 | 28/12 | 6 | 2.5 | 100
TOTAL |  |  | 98 |  |  |  | 226

## P0-P3_Matrix
Severity / Priority Matrix (P0–P3)
Priority | Definition / Examples | Response Expectations | Acknowledge Target | Resolution Target | Postmortem
P0 | Critical platform outage OR Tier-0 source down; data loss risk; security incident. | Page on-call immediately; war room; updates every 30–60 mins; postmortem required. | <=15 mins | Restore/mitigate ASAP | Required
P1 | Major Tier-1 source failing; SLA breach likely within hours; widespread partial failure; severe but recoverable corruption. | Page on-call per coverage; mitigation same day; PIR required if customer impact. | <=30 mins | Same day | Usually
P2 | Non-critical source failing repeatedly; freshness lag breach for Tier-2; elevated 429s but auto-recovering; schema changes quarantined. | Ticket + notify owner; fix within agreed SLA (e.g., 3–5 business days). | <=4 hrs (biz) | 3–5 biz days | Optional
P3 | Cosmetic/non-urgent: dashboard tweaks, transient one-off recovered failures, small enhancements. | Backlog grooming; schedule into sprint. | N/A | Planned | No

## Gantt
Gantt (key tasks & milestones)
This view pulls Start/End week from the Master sheet via INDEX/MATCH.
Task ID | Task Name | Category | Workstream | Start Week | End Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
IMP-55 | Architecture review & signoff | Implementation | Architecture | 3 | 3
IMP-56 | Security design review & signoff | Implementation | Security | 7 | 7
IMP-57 | MVP engine end-to-end demo (2 sources) | Implementation | MVP | 8 | 8
IMP-39 | 42 | 42 | 42 | 42 | 42
IMP-58 | 42 | 42 | 42 | 42 | 42
IMP-41 | 42 | 42 | 42 | 42 | 42
IMP-43 | 42 | 42 | 42 | 42 | 42
IMP-03 | Implement registry Delta tables (sources/endpoints/state/runs/errors) | Implementation | Control Plane | 3 | 4
IMP-05 | Build connector SDK base package | Implementation | Connector SDK | 3 | 4
IMP-07 | Implement connector template: OAuth2 client credentials | Implementation | Connector SDK | 4 | 4
IMP-08 | Implement HTTP client with retries/backoff/jitter | Implementation | Runtime | 4 | 4
IMP-13 | Create Bronze databases/schemas and naming conventions | Implementation | Bronze | 4 | 4
IMP-15 | Integrate external secret manager with Databricks secret scopes | Implementation | Security | 4 | 4
IMP-18 | Implement CI pipeline (tests, lint, packaging) | Implementation | DevSecOps | 4 | 5
IMP-09 | Implement pagination strategies | Implementation | Runtime | 5 | 5
IMP-10 | Implement incremental load strategies + checkpointing | Implementation | Runtime | 5 | 6
IMP-14 | Implement Bronze writer (Delta) with metadata columns | Implementation | Bronze | 5 | 6
IMP-16 | Implement auth handlers (OAuth2/API key) in runtime | Implementation | Security | 5 | 5
IMP-17 | Implement service principals for jobs + UC permissions | Implementation | Security | 5 | 5
IMP-20 | Implement controller workflow (fan-out per source/endpoint) | Implementation | Orchestration | 6 | 7
IMP-22 | 42 | 42 | 42 | 42 | 42
IMP-61 | 42 | 42 | 42 | 42 | 42
IMP-34 | Implement UC permission templates (by classification/tier) | Implementation | Governance | 7 | 7
IMP-23 | 42 | 42 | 42 | 42 | 42
IMP-33 | Publish Policies & Processes set (approved) | Implementation | Governance | 8 | 9
IMP-36 | 42 | 42 | 42 | 42 | 42
IMP-25 | 42 | 42 | 42 | 42 | 42
IMP-40 | 42 | 42 | 42 | 42 | 42
IMP-49 | 42 | 42 | 42 | 42 | 42
IMP-51 | 42 | 42 | 42 | 42 | 42
IMP-52 | 42 | 42 | 42 | 42 | 42